AIRSHOW RAMP LAYOUT DESIGNER

SaaS Project Plan

Sprint-by-Sprint Delivery Schedule  |  Phase 4 — SaaS Platform  |  Version 1.0

| Document Title | ARLD Project Plan |
| --- | --- |
| Project | Airshow Ramp Layout Designer (ARLD) |
| Version | 1.0 |
| Prepared By | Program Management Office |
| Date | May 2026 |
| Sprint Cadence | 2 weeks per sprint |
| Phases Covered | Phase 0 (PoC) through Phase 4 (SaaS) |
| Classification | Confidential — Internal Use Only |

Version 1.0  |  May 2026  |  FOR INTERNAL USE ONLY

PHASE 4 — SaaS Platform (Pending Steering Committee Approval) Relative months +1 to +8 ¦ Sprints 4-1 through 4-4 ¦ Cloud-hosted web application, user accounts, subscription billing

Phase 4 Notice: Phase 4 sprints cannot begin until the Phase 3 gate criteria are met and the steering committee approves the Phase 4 business case with dedicated funding. Sprint dates are relative to the Phase 4 kickoff date (designated month +0).

| Sprint 4-1 | Dates Month +1 to +2 | Points 48 | Sprint Goal: Architecture ADR, WebAssembly PoC vs REST benchmark, React canvas prototype |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 4-1-1 | Author Phase 4 Architecture Decision Record: benchmark WebAssembly (Emscripten) vs REST microservice on 100-aircraft edit workload; select strategy | TRD-SAAS-001 FRD SAAS-003 | Lead C++ Eng + Web Lead | 13 | ADR document filed in repo; benchmark results show latency and bundle size for both strategies; strategy selected |
| 4-1-2 | Scaffold TypeScript/React web application with Vite; configure ESLint, Prettier, Vitest | TRD-SAAS-003 | Web Lead | 3 | React app builds; Vitest smoke test passes; linting CI job green |
| 4-1-3 | Implement React canvas prototype: basic QGraphicsScene equivalent using HTML5 Canvas or Konva.js; pan and zoom | FRD SAAS-001 | Web Lead + Frontend Eng | 8 | Canvas pans and zooms smoothly in Chrome, Edge, Firefox, Safari (current + prior major versions) |
| 4-1-4 | Integrate geometry engine via selected strategy (WASM or REST); verify Minkowski sum result matches desktop output | TRD-SAAS-001 FRD SAAS-003 | Lead C++ Eng + Web Lead | 13 | Web canvas shows identical clearance zone polygon to desktop for same aircraft placement; test fixture passes |
| 4-1-5 | Set up AWS infrastructure: ECS Fargate cluster, ECR, S3 bucket, RDS PostgreSQL 16 Multi-AZ, Redis | TRD-SAAS-007 TRD-SAAS-010 | Cloud Eng | 8 | terraform apply succeeds; ECS task starts; RDS accessible; S3 bucket with SSE-S3 configured |
| 4-1-6 | Configure Auth0 tenant; implement JWT RS256 validation middleware in Fastify; protect /api/v1/ routes | TRD-SAAS-004 FRD SAAS-010–012 | Web Lead | 5 | Unauthenticated request returns HTTP 401; authenticated request with valid JWT returns HTTP 200 |

| Sprint 4-2 | Dates Month +2 to +4 | Points 52 | Sprint Goal: User accounts, project CRUD, cloud sync, team workspaces |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 4-2-1 | Implement user registration/login: email+password and OAuth 2.0 (Google, Microsoft) via Auth0; TLS 1.3 | FRD SAAS-010–012 | Web Lead | 5 | User can register and log in via email and Google OAuth; session uses TLS 1.3 |
| 4-2-2 | Implement MFA (TOTP via Auth0 Guardian); make optional but available to all users | FRD SAAS-013 | Web Lead | 3 | User can enrol TOTP; subsequent logins require OTP; recovery codes generated |
| 4-2-3 | Implement project CRUD API (/api/v1/projects): create, read, update, delete; S3 storage with pre-signed URLs | TRD-SAAS-005 FRD SAAS-030 | Backend Eng | 8 | Project file stored in S3 at {org_id}/{project_id}/{version_id}.arld with SSE-S3 AES-256; pre-signed URL expires in 15 min |
| 4-2-4 | Implement auto-save: web client POSTs JSON Patch diff to /api/v1/projects/{id}/edits ≤ 5 s debounce | TRD-SAAS-006 FRD SAAS-031 | Web Lead + Backend Eng | 8 | Edit diff applied server-side; concurrent edits resolved last-write-wins at field level; no data loss on disconnect |
| 4-2-5 | Implement team workspaces: create workspace, invite members by email, assign roles (Show Director, Ramp Coordinator, Read-Only) | FRD SAAS-020 FRD SAAS-021 | Backend Eng | 8 | Invited user receives email; accepts invite; can view workspace projects per assigned role |
| 4-2-6 | Implement read-only time-limited share link (24-hour expiry, no account required) | FRD SAAS-022 | Backend Eng | 5 | Share link opens read-only canvas in unauthenticated browser; link expires after 24 hours |
| 4-2-7 | Implement full audit log: user_id (UUID), timestamp, action type; PII excluded from logs; pgcrypto column-level encryption for email/org_name | TRD-SAAS-009 FRD SAAS-023 | Backend Eng | 8 | Audit log records every project edit; grep for email in logs returns zero results; pgcrypto functions active |
| 4-2-8 | Implement project archive export: .zip of all .arld files; user data portability | FRD SAAS-033 | Backend Eng | 3 | User can download .zip containing all their projects as .arld files; zip is valid |
| 4-2-9 | ECS auto-scaling: configure ALB RequestCountPerTarget > 1000 scale-out; min 2 tasks, max 50 | TRD-SAAS-007 | Cloud Eng | 5 | Load test: 1,200 concurrent requests → third task spins up within 60 seconds |

| Sprint 4-3 | Dates Month +4 to +6 | Points 50 | Sprint Goal: Stripe billing, SaaS feature parity with desktop, circuit breaker, beta SaaS launch |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 4-3-1 | Implement Stripe subscription billing: free community tier (3 projects, 500 MB) and Pro tier (unlimited); annual discount | FRD SAAS-040–043 TRD-SAAS-009 | Web Lead + Backend Eng | 8 | Test payment succeeds; Pro tier unlocks; no payment card data stored in ARLD DB; Stripe webhook verified |
| 4-3-2 | Implement circuit breaker (opossum) for REST geometry microservice calls; 50% error threshold; HTTP 503 + Retry-After | TRD-SAAS-008 | Backend Eng | 5 | Simulated geometry service failure → circuit opens after 50% error rate; clients receive 503 with Retry-After header |
| 4-3-3 | Implement SaaS feature parity: all 7 display types, all clearance rules, violation overrides, layout versioning, all 4 export formats in web UI | FRD SAAS-001 Charter SaaS parity | Web Lead + Frontend Eng | 13 | Web app produces identical SVG/PDF/PNG/JPEG output to desktop for same reference layout |
| 4-3-4 | Implement automated RDS failover test; confirm RTO ≤ 15 min; enable 14-day automated backups | TRD-SAAS-010 FRD SAAS-053 | Cloud Eng | 5 | Simulated primary AZ failure → app reconnects to replica within 15 min; no data loss; backup retention confirmed |
| 4-3-5 | Perform SaaS security audit and penetration test (external firm); remediate all critical and high findings | Charter Phase 4 budget | Cloud Eng + External | 13 | Penetration test report received; all critical/high findings remediated; retest passed |
| 4-3-6 | Launch beta SaaS (invite-only, 50 users); set up uptime monitoring (99.5% SLA target) | Charter Phase 4 Milestone | PM + Cloud Eng | 3 | 50 beta users active; uptime dashboard live; no outage > 15 min in first 2 weeks |
| 4-3-7 | Implement responsive design for tablet screens (minimum 1024×768); test on iPad and Android tablet | FRD SAAS-004 | Frontend Eng | 3 | Canvas usable on iPad 10th gen and Samsung Galaxy Tab S8; no horizontal scroll on 1024 px viewport |

| Sprint 4-4 | Dates Month +6 to +8 | Points 44 | Sprint Goal: Public SaaS v1.0 launch, 99.5% uptime SLA, post-launch monitoring |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 4-4-1 | Implement desktop ↔ SaaS bidirectional sync: .arld projects started on desktop continue in browser and vice versa | FRD SAAS-032 | Web Lead + Lead C++ Eng | 13 | Round-trip: create layout on desktop → sync → open in browser → edit → sync back → open on desktop; no data loss |
| 4-4-2 | Public SaaS v1.0 launch: open registration; publish pricing page; announce to ICAS community | Charter Phase 4 Milestone | PM + Web Lead | 5 | Public registration open; first 100 free-tier sign-ups within first week; pricing page live |
| 4-4-3 | Confirm 99.5% uptime SLA during peak planning period (simulate October load test) | FRD SAAS-051 TRD-SAAS-007 | Cloud Eng + QA Eng | 8 | Load test: 10,000 concurrent sessions; P95 response time < 500 ms; uptime 99.5%+ over 30-day window |
| 4-4-4 | Implement SaaS KPI tracking: registered events, Pro conversions, NPS survey at 30-day mark | Charter §13 Phase 4 KPIs | PM | 3 | KPI dashboard live; first 30-day NPS survey sent; 100 registered events target tracked |
| 4-4-5 | Take manual RDS snapshot before production launch; confirm 14-day automated backups active | TRD-SAAS-010 | Cloud Eng | 2 | Manual snapshot exists pre-launch; automated backup schedule verified in AWS console |
| 4-4-6 | Phase 4 retrospective; finalise Phase 4 budget actuals; publish SaaS launch post-mortem | Charter §14.2 | PM | 3 | Retrospective report filed; budget within estimate; post-mortem published to engineering blog |
| 4-4-7 | Reach 100 registered events KPI (12-month target); or file remediation plan with steering committee | Charter §13 KPI SaaS 100 events | PM | 5 | 100 registered events milestone confirmed in dashboard; or growth-gap remediation plan filed |
| 4-4-8 | Post-launch security monitoring: enable AWS GuardDuty, CloudTrail, WAF rules; set up PagerDuty on-call rotation | TRD-SAAS-007 Charter Security | Cloud Eng | 5 | GuardDuty active; CloudTrail logs shipping to S3; on-call rotation confirmed with < 5 min escalation |

⭐ Phase 4 Launch Criteria (Month +8) - Public SaaS v1.0 live; open registration; pricing page published - 99.5% uptime confirmed over rolling 30-day window - 10,000 concurrent session load test passed (P95 response < 500 ms) - Desktop ⇔ SaaS bidirectional sync functional; round-trip data integrity verified - External penetration test passed; all critical/high findings remediated - 100 registered events target tracked (12-month KPI runway established) - AWS GuardDuty, CloudTrail, and WAF active; on-call rotation in place

Desktop phases (0–3) are documented in ARLD_Project_Plan_v1.0.docx. Phase 4 cannot begin until the Phase 3 gate criteria are met and the steering committee approves the Phase 4 business case.

# Velocity and Capacity Summary

The table below summarises planned story points, team size, and key outcomes per sprint across all phases. Phase 4 team size is indicative pending Phase 4 staffing plan.

| Sprint | Planned Pts | Team Size | Velocity | Key Outcome |
| --- | --- | --- | --- | --- |
| Sprint 4-1 | 48 | 6.0 FTE* | 48 | ADR; WASM/REST benchmark; React canvas PoC |
| Sprint 4-2 | 52 | 7.0 FTE* | 52 | Auth; project CRUD; cloud sync; workspaces |
| Sprint 4-3 | 50 | 7.0 FTE* | 50 | Stripe billing; SaaS parity; beta SaaS launch |
| Sprint 4-4 | 44 | 7.0 FTE* | 44 | Desktop sync; public SaaS v1.0; uptime SLA |

* Phase 4 team size is indicative; finalised as part of the Phase 4 staffing plan approved at Phase 3 gate.

| Phase | Total Sprints | Total Planned Points | Duration |
| --- | --- | --- | --- |
| Phase 4 — SaaS (pending) | 4 | 194 | 8 months relative to Phase 4 kickoff |

# Authorization and Approval

By signing below, the undersigned approve this Project Plan as the governing sprint schedule for the Airshow Ramp Layout Designer project.

| _________________________________ Director of Airshow Operations Signature / Date | _________________________________ Program Management Officer Signature / Date | _________________________________ Lead Systems Engineer Signature / Date |
| --- | --- | --- |

— End of Document —