AIRSHOW RAMP LAYOUT DESIGNER

Project Charter  —  Version 2.0

Precision Ramp Planning for Safe, Compliant, and Spectacular Airshows

Now featuring a C++ cross-platform proof-of-concept for Mac, Linux, and Windows

| Project Name | Airshow Ramp Layout Designer (ARLD) |
| --- | --- |
| Document Type | Project Charter |
| Version | 2.0 — C++ PoC + SaaS Phase Addition |
| Supersedes | Version 1.0 (May 2026) |
| Prepared By | Program Management Office |
| Date | May 2026 |
| Classification | Confidential — Internal Use Only |
| Approving Authority | Director of Airshow Operations |

Version 2.0  |  May 2026  |  FOR INTERNAL USE ONLY

# Document Change History

| Version | Date | Author | Summary of Changes |
| --- | --- | --- | --- |
| 1.0 | May 2026 | PMO | Initial release |
| 2.0 | May 2026 | PMO | Added Phase 0 (C++ PoC); restructured Phases 1–3; moved SaaS to Phase 4; updated architecture, budget, milestones, and risk register. |

# 1. Executive Summary

The Airshow Ramp Layout Designer (ARLD) is a specialized application that enables airshow directors, ramp coordinators, and ground operations personnel to design, visualize, and publish precise aircraft parking and display layouts for static and flying airshows.

Version 2.0 of this charter introduces a phased delivery model that begins with a C++ proof-of-concept (PoC) desktop application built entirely on open-source components and compilable natively on macOS, Linux, and Windows. This PoC phase de-risks the core geometry and rendering engine before any web or cloud investment is made. The subsequent phases deliver a full-featured cross-platform desktop product, followed by an optional SaaS tier as a separate, independently funded phase.

Airshow ramp planning is a safety-critical activity. Incorrectly spaced aircraft can create Foreign Object Debris (FOD) hazards, impede emergency egress routes, violate FAA Certificate of Waiver (CoW) separation requirements, and diminish the spectator experience. Current workflows rely on hand-drawn sketches, generic CAD tools, or spreadsheets — none of which provide real-time scaling, aircraft-type awareness, or standards-compliance checking.

ARLD addresses this gap by providing a purpose-built visual design environment where every aircraft silhouette, parking node, and service lane is rendered at true geographic scale. The application will export finished layouts in SVG, PDF, PNG, and JPEG formats suitable for printed briefing packages and digital distribution.

# 2. Project Overview

## 2.1  Background and Need

Major airshow events host between 20 and 200+ static display aircraft across ramp areas ranging from 5 to more than 100 acres. Coordinating the physical placement of aircraft spanning 20 feet (ultralight) to 222 feet (B-52H) within a shared apron — while maintaining required wingtip clearances, fuel-safe separation distances, spectator barriers, and emergency access corridors — demands spatially accurate planning tools.

Industry surveys from the 2025 ICAS convention identified ramp layout planning as one of the top three administrative pain points for show directors. Existing tools produce diagrams that cannot be reprinted at consistent scale, do not flag clearance violations, and require manual rework each season even when the same aircraft types return.

## 2.2  Vision Statement

ARLD will become the authoritative, community-supported standard for airshow ramp planning — delivering the accuracy of an engineering CAD tool in an interface accessible to non-technical airshow operations staff, starting from an open-source C++ foundation that runs on any major operating system.

## 2.3  Revised Delivery Strategy

v2.0 Change: The project now follows a four-phase model. Phase 0 is a time-boxed C++ proof-of-concept. Phases 1–3 build the full desktop product. Phase 4 delivers the SaaS / cloud tier as a separate, independently approved effort.

Phase 0 — C++ Proof of Concept (new): A 10-week, open-source-only PoC that validates core technology choices (rendering engine, geometry, export pipeline) on macOS, Linux, and Windows without any cloud or subscription dependency.

Phase 1 — Foundation: Core desktop application (C++ production quality), full aircraft library (150+ types), and all display/clearance logic.

Phase 2 — Complete Desktop Product: Full export suite (SVG, PDF, PNG, JPEG), layout versioning, offline operation, and UAT with real airshow events.

Phase 3 — Desktop Launch: Public v1.0 desktop release, open-source community edition, and commercial desktop license tier.

Phase 4 — SaaS Platform (separate phase): Cloud-hosted web application, user accounts, cloud sync, API integrations, and subscription billing. Requires separate business case and steering committee approval before initiation.

## 2.4  Project Objectives

- Deliver a C++ PoC within 10 weeks that compiles and runs on macOS, Linux, and Windows using only open-source libraries.

- Demonstrate scaled aircraft placement with clearance checking and SVG export in the PoC.

- Evolve the PoC into a full-featured desktop application (Phases 1–3) with a library of 150+ aircraft types.

- Enforce configurable clearance rules (FAA CoW defaults plus user-defined) in real time.

- Export finished layouts in SVG, PDF (A-size through E-size), PNG, and JPEG with selectable resolution and scale bar.

- Achieve a first-time-user task-completion rate of ≥85% for a standard 30-aircraft layout within 60 minutes.

- Establish a SaaS platform in Phase 4, contingent on Phase 3 desktop adoption metrics and separate funding approval.

# 3. Project Scope

## 3.1  Phase 0 — C++ PoC Scope

Scope boundary: Phase 0 is intentionally narrow. Its sole purpose is to prove the technology stack. No production-quality polish, user accounts, or cloud connectivity is required.

- CMake-based build system; single command build on macOS (Clang), Linux (GCC/Clang), and Windows (MSVC / MinGW)

- Interactive 2D canvas using Qt 6 (open-source LGPL) with pan, zoom, and snap-to-grid

- Hardcoded library of 20 representative aircraft types covering all major categories

- Drag-and-drop placement of scaled aircraft silhouettes (top-down SVG outlines)

- Clearance-zone rendering for wingtip and propeller arc using configurable minimums

- Real-time violation highlighting (green/yellow/red overlay)

- SVG export of the current canvas view via nanosvg or Qt SVG

- Basic ramp boundary polygon definition (draw or numeric input)

- Single-file project save/load using JSON (nlohmann/json)

- No user authentication, no cloud connectivity, no subscription management

- PoC source code published to an internal Git repository with an open-source license (Apache 2.0)

## 3.2  Phase 1–3 Desktop Scope (In Scope)

- Production C++ application evolved from the PoC codebase

- Qt 6 desktop application with full installer for macOS (.dmg), Linux (.AppImage / .deb), and Windows (.msi)

- Aircraft library expanded to 150+ types with accurate dimensional data

- All seven display categories with type-specific clearance logic

- Satellite/aerial photograph underlay with opacity control

- Complete export suite: SVG, PDF (Letter–ANSI-E1), PNG (72–600 DPI), JPEG

- Layout versioning and change-delta highlighting

- Offline operation — no network required for core functionality

- Auto-update mechanism for aircraft library data

- Per-aircraft metadata (tail number, owner, arrival/departure, fuel type, hazmat)

- Community edition (open-source, free) and commercial desktop license tier

## 3.3  Phase 4 — SaaS Scope (Separate Phase — Pending Approval)

Phase 4 notice: The SaaS platform is a separately funded and governed phase. It will not be initiated until the Phase 3 desktop product achieves defined adoption milestones and the steering committee approves a Phase 4 business case.

- Web application (TypeScript / React) consuming a REST API backed by the C++ geometry engine

- Node.js / Fastify API layer; AWS ECS (Fargate) cloud hosting

- User accounts, team workspaces, and project cloud sync

- Subscription billing via Stripe (free community tier + pro tier)

- Public API for integration with third-party show-management platforms

- 99.5% uptime SLA; 10,000 concurrent session scalability target

## 3.4  Out of Scope (All Phases)

- Three-dimensional or isometric aircraft rendering

- Real-time GPS tracking of actual aircraft positions

- Flight-line (aerobatic box) or airspace planning

- Fuel, weight, and balance calculations

- Crew scheduling or volunteer management

- Integration with FAA OEAAA or NOTAM filing systems (future consideration)

# 4. Stakeholders

| Stakeholder / Group | Role | Engagement Level |
| --- | --- | --- |
| Airshow Directors | Primary end users; define ramp layout requirements | High — Sprint reviews, UAT |
| Ramp Coordinators | Day-of operators; validate clearance and spacing | High — PoC field testing |
| FAA Flight Standards | Regulatory authority; CoW clearance requirements | Consultative |
| ICAS Safety Committee | Industry standards body; best-practice guidance | Consultative |
| Aircraft Owners/Exhibitors | Supply aircraft dimensions and parking needs | Medium — Data validation |
| Open-Source Community | PoC and community-edition contributors; bug reporters | Medium — GitHub collaboration |
| Show Production Companies | Package layouts into printed programs | Medium — Export format review |
| IT / Platform Engineering | Infrastructure, CI/CD, cloud hosting (Phase 4) | High — Internal team |
| Legal / Compliance | IP, open-source license compliance, data privacy | Medium — License gate review |

# 5. Phase 0 — C++ PoC Technical Design

## 5.1  Design Goals

The PoC is governed by three principles: open-source only (no proprietary SDKs or cloud services), native compilation on the three major OS platforms without emulation or compatibility layers, and a codebase structured to evolve directly into the Phase 1 production application.

## 5.2  Open-Source Component Stack

| Component | Library / Version | Purpose |
| --- | --- | --- |
| Build System | CMake 3.28+ | Cross-platform build; generates Xcode, Ninja, and MSVC project files from one CMakeLists.txt |
| GUI / Canvas | Qt 6.7 (LGPL) | Cross-platform windowing, 2D graphics (QPainter / QGraphicsView), event loop, and high-DPI support |
| Geometry Engine | CGAL 5.6 (GPL/LGPL) | Computational geometry: polygon union, Minkowski sum for clearance zones, convex hull |
| SVG Export | Qt SVG module | Vector SVG output of the canvas; also used for importing aircraft silhouette files |
| PDF Export | libharu 2.4 (MIT) | Programmatic PDF generation; supports A through E paper sizes with embedded fonts |
| Raster Export | stb_image_write (MIT) | Header-only PNG and JPEG export at configurable DPI |
| JSON / File Format | nlohmann/json 3.11 (MIT) | Project file serialization; aircraft library format; settings persistence |
| Unit Testing | Catch2 3.x (BSL-1.0) | Cross-platform C++ test framework; integrated with CTest for CI pipeline |
| CI / CD | GitHub Actions | Build matrix: ubuntu-latest (GCC 13), macos-14 (Clang 16 / Apple Silicon), windows-latest (MSVC 2022) |
| Package Manager | vcpkg (MIT) | Manages all third-party C++ dependencies; manifest mode for reproducible builds |

License note: All PoC dependencies are permissively licensed (MIT, BSL) or LGPL. Qt 6 LGPL permits dynamic linking without copyleft obligations. CGAL modules used in the PoC are LGPL; GPL components are not included.

## 5.3  Repository and Build Structure

The repository will be organized as a single CMake super-project with clearly separated modules to facilitate the Phase 1 evolution:

- arld/core/ — Platform-independent geometry, clearance engine, aircraft library parser, and project file I/O

- arld/ui/ — Qt-based canvas, toolbar, property panels, and dialogs

- arld/export/ — SVG, PDF, PNG, and JPEG export pipeline

- arld/data/ — Aircraft library JSON files and silhouette SVG assets

- arld/tests/ — Catch2 unit and integration tests

- CMakePresets.json — Standard presets for debug/release on each platform

A single command — cmake --preset release && cmake --build --preset release — shall produce a runnable application binary on all three platforms with no additional manual steps beyond installing system prerequisites (documented in README.md).

## 5.4  PoC Acceptance Criteria

The Phase 0 PoC will be considered complete when all of the following are verified:

- GitHub Actions CI passes clean builds on all three matrix targets (macOS Apple Silicon, Ubuntu 22.04, Windows Server 2022).

- 20 aircraft types are populated in the library with correct scaled silhouette rendering.

- A test ramp layout with 15 aircraft can be created, saved, reloaded, and exported to SVG with no data loss.

- Clearance violations are correctly detected and highlighted for at least five violation scenarios defined in the test suite.

- A domain expert (airshow ramp coordinator) can complete a basic 10-aircraft layout within 20 minutes without assistance.

- No GPL-licensed code is present in the deliverable binaries (verified by license-checker CI step).

# 6. Functional Requirements

## 6.1  Ramp Canvas

- The canvas shall render a user-defined ramp boundary at selectable scales from 1:200 to 1:5000.

- The canvas shall support a satellite/aerial photograph underlay with opacity control.

- The canvas shall display a dynamic scale bar, north arrow, and coordinate grid overlay (togglable).

- Pan and zoom shall be smooth at 60 fps on hardware meeting minimum specifications.

- The canvas shall support undo/redo of all placement actions (minimum 100 levels).

## 6.2  Aircraft Library

- Phase 0: 20 representative types across all major categories.

- Phase 1: 150+ types with full dimensional data (wingspan, length, height, turning radius, prop/rotor arc).

- Each entry shall include manufacturer, model/variant, category, and clearance parameters.

- Aircraft silhouettes shall be SVG vector outlines scaled to exact published dimensions.

- Users shall be able to add custom aircraft entries with manually entered dimensions.

## 6.3  Aircraft Placement and Display Types

Each aircraft placed on the ramp shall be assigned one of the following display types:

  - Static Display — 25-ft minimum wingtip clearance (FAA default).

  - Static Display — Warbird/Heritage — Additional 10-ft propeller arc clearance.

  - Taxi-Only — 50-ft corridor required.

  - Military Static — Enhanced security perimeter; default 50-ft stand-off.

  - Hot Ramp — Fueling active; 100-ft no-smoking radius rendered automatically.

  - Media/Photo Platform — Crush-barrier overlay.

  - Ramp Show Aircraft — 200-ft crowd-line clearance applied.

- Aircraft shall be rotatable in 1-degree increments with snap-to-45 and snap-to-heading options.

- Placement shall trigger real-time clearance checks against all adjacent aircraft and zone boundaries.

## 6.4  Clearance Checking

- The system shall compute and display per-aircraft clearance zones as colored overlays (green/yellow/red).

- A violations panel shall list all active issues with aircraft identifiers, violation type, measured gap, and required minimum.

- Users shall be able to configure custom clearance rules per show and override individual violations with a documented justification.

- Clearance computations shall account for propeller arcs, rotor discs, tail-dragger tail-swing, and retracted/extended gear.

## 6.5  Export

- SVG — Full-fidelity scalable vector; all layers; suitable for web and vector editing tools.

- PDF — Print-ready; paper sizes Letter through ANSI-E1; embedded fonts; CMYK-safe; title block, legend, and scale bar.

- PNG — Rasterized at 72–600 DPI; transparent or white background; optional scale bar.

- JPEG — Rasterized at 72–600 DPI, quality 60–100%; white background.

- All formats shall honor layer visibility at export time.

- Batch export shall produce all four formats simultaneously.

# 7. Non-Functional Requirements

| Category | Requirement |
| --- | --- |
| Performance | Canvas renders 200+ aircraft at 60 fps on a modern laptop (Intel i5 / AMD Ryzen 5, 8 GB RAM, integrated graphics) on all three platforms. |
| Portability | All C++ code shall conform to C++20 standard. No platform-specific APIs outside Qt abstraction layer. Single CMakeLists.txt drives all three platform builds. |
| Open Source | Phase 0 and the community desktop edition shall be Apache 2.0 licensed. No GPL dependencies in distributable binaries. All transitive licenses documented in LICENSES.txt. |
| Reliability | Desktop application shall handle abrupt close without data loss (auto-save every 60 seconds to a temp file). Zero crash rate on the PoC acceptance test suite. |
| Security | No network connections in Phase 0–3 desktop builds except optional library update check (opt-in). No telemetry without explicit user consent. |
| Usability | UI shall conform to WCAG 2.1 AA. Supports Windows 10/11, macOS 12+, Ubuntu 22.04 LTS, Fedora 38+. |
| Maintainability | Code coverage ≥80% for core geometry and clearance modules. Architecture Decision Records (ADRs) maintained for all major design choices. |
| Localization | Metric (m) and imperial (ft) unit systems switchable per project. |
| Data Portability | Project files use open JSON-based .arld format with published schema; full round-trip import/export guaranteed across platform builds. |

# 8. Technical Architecture Overview

## 8.1  Phase 0–3 Desktop Architecture (C++)

- Language: C++20 (Clang 16+, GCC 13+, MSVC 2022)

- GUI Framework: Qt 6.7 LGPL — QGraphicsView for canvas, Qt SVG for silhouettes, Qt Print Support for PDF

- Geometry Engine: CGAL 5.6 (LGPL subset) — polygon clipping, Minkowski sums for clearance envelopes

- PDF Export: libharu 2.4 (MIT) — programmatic PDF generation with embedded fonts and ICC profiles

- Raster Export: stb_image_write (MIT) — PNG and JPEG at configurable DPI

- JSON / Persistence: nlohmann/json 3.11 (MIT) — project files and aircraft library

- Build: CMake 3.28 + vcpkg manifest mode — reproducible dependency resolution

- Testing: Catch2 3 + CTest — unit and integration tests; run in CI on all three platforms

- Packaging: CPack — .dmg (macOS), .AppImage + .deb (Linux), .msi (Windows)

## 8.2  Phase 4 SaaS Architecture (Separate Phase)

Phase 4 only: The following components apply exclusively to the Phase 4 SaaS platform and are not part of the desktop application build.

- Frontend: TypeScript, React, consuming C++ geometry engine via WebAssembly (Emscripten) or REST microservice

- API Layer: Node.js + Fastify, deployed on AWS ECS Fargate

- Database: PostgreSQL 16 (project/user data), Redis (session cache)

- Storage: AWS S3 (project files, exports, satellite underlays)

- Auth: Auth0 (OIDC/OAuth 2.0)

- Billing: Stripe subscriptions

- Export Service: Server-side headless Qt or Puppeteer for PDF/PNG rendering

## 8.3  Cross-Platform Build Matrix

| Platform | Compiler / Toolchain | CI Runner | Package Format |
| --- | --- | --- | --- |
| macOS 12+ (Intel & Apple Silicon) | Apple Clang 16 / Xcode 15 | macos-14 (GitHub Actions) | .dmg (CPack) |
| Linux — Ubuntu 22.04 LTS | GCC 13 / CMake Ninja | ubuntu-22.04 | .AppImage + .deb |
| Linux — Fedora 38+ | GCC 13 | Container (Fedora 38) | .rpm (CPack) |
| Windows 10/11 (x64) | MSVC 2022 (v143 toolset) | windows-2022 | .msi (WiX Toolset) |

# 9. Project Phases and Milestones

The project is organized into five phases. Phase 0 is time-boxed to 10 weeks. Phases 1–3 build the complete desktop product. Phase 4 (SaaS) requires a separate gate approval.

Phase 0 — C++ Proof of Concept  (Weeks 1–10)

| Week | Milestone | Target | Deliverable |
| --- | --- | --- | --- |
| Week 1–2 | Repository scaffold; CMake + vcpkg baseline; CI green on all 3 platforms | Week 2 | CI pipeline, README build instructions |
| Week 3–4 | Qt canvas prototype: pan, zoom, snap grid, ramp polygon draw | Week 4 | Interactive canvas demo |
| Week 5–6 | 20-aircraft library; scaled SVG silhouettes; drag-and-drop placement | Week 6 | Aircraft library v0.1 |
| Week 7–8 | CGAL clearance zones; real-time violation highlighting | Week 8 | Clearance engine v0.1 |
| Week 9 | SVG export; JSON project save/load; undo/redo | Week 9 | Export pipeline v0.1 |
| Week 10 | PoC acceptance test; domain expert usability session; gate review | Week 10 | PoC sign-off report |

Phase 1 — Foundation  (Months 3–6)

| Month | Milestone | Target | Deliverable |
| --- | --- | --- | --- |
| Month 3 | PoC-to-production refactor; installer scaffolding for 3 platforms | Month 3 | Installable alpha on all platforms |
| Month 4 | Aircraft library expanded to 75 types; metadata fields | Month 4 | Library v0.5 |
| Month 5 | All 7 display types and zone definitions; violation override workflow | Month 5 | Feature-complete alpha |
| Month 6 | Satellite underlay; coordinate grid; layout versioning | Month 6 | Alpha release to 10 beta users |

Phase 2 — Complete Desktop Product  (Months 7–12)

| Month | Milestone | Target | Deliverable |
| --- | --- | --- | --- |
| Month 7 | Full aircraft library (150+ types); SVG and PDF export complete | Month 7 | Export module v1; Library v1.0 |
| Month 8 | PNG and JPEG export; batch export; scale bar variants | Month 8 | All export formats complete |
| Month 9 | Per-aircraft metadata; auto-save; offline operation verified | Month 9 | Beta release |
| Month 10 | Auto-update mechanism for library data | Month 10 | Update service v1 |
| Month 11 | UAT with 3 real airshow events; bug fix sprint | Month 11 | UAT sign-off report |
| Month 12 | Security review; open-source license audit; performance benchmarks | Month 12 | Audit reports |

Phase 3 — Desktop Launch  (Month 13–14)

| Month | Milestone | Target | Deliverable |
| --- | --- | --- | --- |
| Month 13 | Public v1.0 desktop release (all platforms); open-source community edition on GitHub | Month 13 | Production release + GitHub repo |
| Month 14 | Commercial license tier; ICAS marketplace listing; adoption dashboard | Month 14 | Commercial launch |

Phase 4 — SaaS Platform  (Initiation Pending Steering Committee Approval)

Gate requirement: Phase 4 cannot begin until the following are met: (1) 50+ active airshow events using the v1.0 desktop product, (2) NPS ≥ 40 from show directors, and (3) written Phase 4 business case approved by the steering committee with dedicated funding.

| Month* | Milestone | Target* | Deliverable |
| --- | --- | --- | --- |
| +1 | Phase 4 kickoff; web architecture design; Emscripten / REST API evaluation | +1 mo | Architecture decision record |
| +2 | React web canvas prototype consuming C++ geometry engine | +2 mo | Web PoC demo |
| +4 | User accounts, cloud sync, project sharing | +4 mo | Alpha web app |
| +6 | Subscription billing; SaaS tier feature parity with desktop | +6 mo | Beta SaaS launch |
| +8 | Public SaaS v1.0 launch; 99.5% uptime SLA | +8 mo | Production SaaS |

* Phase 4 month numbers are relative to Phase 4 kickoff, not project start.

# 10. Budget Summary

The budget is structured in two independently authorized tranches: Phases 0–3 (desktop product) and Phase 4 (SaaS platform, pending approval).

## 10.1  Phases 0–3 — Desktop Product Budget

| Budget Category | Estimated Cost (USD) | % of Total |
| --- | --- | --- |
| Phase 0 — C++ PoC (engineering, 10 weeks) | $65,000 | 9% |
| Phase 1–2 Engineering (C++ desktop, QA) | $310,000 | 44% |
| Phase 3 Packaging, Licensing, Launch | $40,000 | 6% |
| Aircraft Library Data Acquisition | $45,000 | 6% |
| UX Design and User Research | $50,000 | 7% |
| CI/CD Infrastructure (GitHub Actions, build hosts) | $12,000 | 2% |
| Third-Party Licenses and APIs (Qt commercial, maps) | $18,000 | 3% |
| Security and Open-Source License Audit | $20,000 | 3% |
| UAT Field Testing (travel/events) | $30,000 | 4% |
| Program Management | $65,000 | 9% |
| Contingency Reserve (10%) | $65,500 | 9% |
| TOTAL — PHASES 0–3 | $720,500 | 100% |

## 10.2  Phase 4 — SaaS Platform Budget (Estimate — Pending Approval)

Budget status: The following is a high-level estimate only. A detailed Phase 4 budget will be produced as part of the Phase 4 business case after Phase 3 launch.

| Budget Category | Estimated Cost (USD) | % of Total |
| --- | --- | --- |
| Web / API Engineering (8 months) | $280,000 | 56% |
| AWS Infrastructure (ECS, RDS, S3, CDN) | $40,000 | 8% |
| Authentication and Billing Integrations | $20,000 | 4% |
| Security Audit and Penetration Test | $25,000 | 5% |
| Program Management | $55,000 | 11% |
| Contingency (15%) | $63,000 | 13% |
| TOTAL — PHASE 4 (ESTIMATE) | $483,000 | 100% |

# 11. Risk Register

| Risk | Probability | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| C++ PoC reveals fundamental performance limitation in Qt canvas at 200+ aircraft | Low | High | Evaluate Vulkan/Metal backend or direct OpenGL fallback before Phase 1 commit; benchmark in Week 5. |
| CGAL license compliance issue discovered during open-source audit | Low | High | Legal review in Week 1; pre-identify MIT-licensed alternative (Clipper2) as drop-in fallback. |
| Aircraft dimensional data inaccuracies from manufacturers | Medium | High | Cross-reference three published sources; user-correction submission portal in Phase 1. |
| Build toolchain fragmentation across macOS / Linux / Windows | Medium | Medium | vcpkg manifest mode + CMakePresets.json enforces identical dependency versions; CI verifies all three platforms on every commit. |
| FAA or ICAS clearance rule changes mid-development | Low | High | Abstract rule engine as JSON-configurable; no hard-coded distances in application binary. |
| Domain expert resistance to adopting new tool (change management) | High | Medium | 3 show directors as design partners from Week 1; migration guide from existing tools; PoC usability session in Week 10. |
| Phase 4 SaaS never funded after desktop launch | Medium | Low | Desktop product is self-contained and commercially viable standalone; SaaS is additive, not required for project success. |
| PDF export fidelity issues across print vendors | Medium | Medium | Test libharu output against top 5 show-printing vendors; embed fonts; produce ICC-tagged PDFs. |
| Key engineer departure causing knowledge loss | Medium | High | Enforce ADRs; pair-program on all critical modules; CMake build is fully documented for new contributors. |

# 12. Assumptions and Constraints

## 12.1  Assumptions

- Qt 6 LGPL dynamic linking satisfies open-source license obligations for the community desktop edition.

- Aircraft dimensional data provided by manufacturers and ICAS is accurate to within ±6 inches.

- FAA CoW clearance minimums will not be revised during Phase 0 or Phase 1 development.

- PoC beta users have access to a modern laptop running macOS 12+, Ubuntu 22.04+, or Windows 10/11.

- The ICAS will grant permission to reference their aircraft library data under a data-sharing agreement.

- Phase 4 adoption gate metrics will be reachable within 6 months of Phase 3 desktop launch.

## 12.2  Constraints

- No GPL-licensed code may be included in distributable application binaries (LGPL is permitted with dynamic linking).

- Aircraft silhouette artwork must be original or licensed; no reproduction of copyrighted manufacturer diagrams.

- The desktop application must not require administrator/root privileges for installation on any supported platform.

- All PII in Phase 4 SaaS must comply with CCPA and GDPR.

- The Phase 3 desktop launch must occur prior to the 2028 airshow season pre-planning period.

# 13. Success Criteria and KPIs

| Phase | Success Criterion | Minimum Target | Stretch Target |
| --- | --- | --- | --- |
| 0 | CI green on all 3 platforms with 0 failing tests | 100% pass | 100% pass + Coverity clean |
| 0 | Domain expert completes 10-aircraft layout without assistance | < 20 min | < 12 min |
| 1–2 | First-time-user task completion rate (30-aircraft layout, 60 min) | 85% | 95% |
| 3 | Active airshow events using ARLD for primary ramp planning (6 mo post-launch) | 25 events | 75 events |
| 3 | Net Promoter Score (NPS) from show directors (6 mo post-launch) | 40 | 65 |
| 3 | Export quality satisfaction rating (PDF/PNG accuracy) | 4.0 / 5.0 | 4.7 / 5.0 |
| 3 | Clearance violation detection accuracy vs. manual review | 98% | 99.9% |
| 4* | SaaS uptime during peak planning periods | 99.5% | 99.9% |
| 4* | SaaS registered events (12 mo post-launch) | 100 events | 300 events |

* Phase 4 KPIs are indicative only and will be finalized as part of the Phase 4 business case.

# 14. Project Team and Governance

## 14.1  Core Team — Phases 0–3

| Role | Allocation | Responsibilities |
| --- | --- | --- |
| Project Manager | 1.0 FTE | Schedule, budget, stakeholder comms, risk, phase gate reviews |
| Lead C++ Engineer | 1.0 FTE | Architecture, canvas engine (Qt/CGAL), export pipeline, CI setup |
| C++ Desktop Engineers | 2.0 FTE | Feature implementation, library browser UI, platform packaging |
| UX Designer | 0.5 FTE | Interaction design, usability testing, design system |
| Data Curator | 0.5 FTE | Aircraft library acquisition, dimensional data validation, SVG silhouettes |
| QA Engineer | 1.0 FTE | Test strategy, Catch2 automation, performance benchmarking |
| Aviation Domain Consultant | 0.25 FTE | FAA/ICAS compliance review, clearance rule validation, PoC usability sessions |

Phase 4 team: A dedicated web/cloud engineering team will be recruited and staffed as part of the Phase 4 business case. Phase 0–3 desktop engineers may optionally transition to Phase 4 roles.

## 14.2  Governance

- Weekly stand-up: engineering team (30 min, async-first)

- Bi-weekly sprint review: core team + product owner (60 min)

- Monthly steering committee: PM, Director of Airshow Operations, Finance (60 min)

- Phase gate reviews: formal go/no-go with documented sign-off — PoC gate at Week 10; Phase 1–3 gates at Phase boundaries; Phase 4 gate requires full business case

- Change control: all scope changes require a written Change Request approved by steering committee

- Open-source governance: all community contributions reviewed via GitHub pull requests; CLA required for external contributors

# 15. Authorization and Approval

By signing below, the undersigned authorize commencement of the ARLD project Phases 0–3 as described in this charter. Phase 4 (SaaS Platform) requires a separate authorization following the Phase 3 desktop launch and gate review.

| _________________________________ Director of Airshow Operations Signature / Date | _________________________________ Program Management Officer Signature / Date | _________________________________ Chief Technology Officer Signature / Date |
| --- | --- | --- |

# Appendix A: Representative Aircraft Library Sample

The following table illustrates the dimensional data format for a sample of aircraft types. Dimensions reflect published manufacturer data or ICAS standards (feet).

| Aircraft | Wingspan (ft) | Length (ft) | Height (ft) | Prop Arc (ft) | Category |
| --- | --- | --- | --- | --- | --- |
| B-52H Stratofortress | 185.0 | 160.9 | 40.8 | N/A (jet) | Military Static |
| C-17A Globemaster III | 169.8 | 174.0 | 55.1 | N/A (jet) | Military Static |
| F-22A Raptor | 44.5 | 62.1 | 16.7 | N/A (jet) | Military Static |
| P-51D Mustang | 37.0 | 32.3 | 13.8 | 12.0 | Warbird |
| B-17G Flying Fortress | 103.9 | 74.4 | 19.1 | 14.0 | Warbird |
| Stearman PT-17 | 32.2 | 25.0 | 9.2 | 8.5 | Warbird |
| Pitts S-2C | 20.0 | 17.9 | 6.5 | 6.0 | Aerobatic |
| Extra 330SC | 26.4 | 22.1 | 8.1 | 7.5 | Aerobatic |
| Cessna 172S | 36.1 | 27.2 | 8.9 | 6.5 | Static Display |
| Cirrus SR22 | 38.3 | 26.0 | 8.9 | 7.0 | Static Display |
| Bell UH-1 Huey | 48.0 | 57.4 | 14.6 | 24.0 (rotor) | Heritage |
| AH-64E Apache | 48.0 | 58.2 | 15.2 | 24.0 (rotor) | Military Static |

# Appendix B: C++ PoC — Getting Started

The following instructions describe the minimum prerequisites and build steps for a developer setting up the PoC on each supported platform.

## Prerequisites — All Platforms

- CMake 3.28 or later

- Git 2.40 or later

- vcpkg (clone from github.com/microsoft/vcpkg and bootstrap)

- Qt 6.7 open-source installer (select Qt 6.7.x for your platform)

## macOS

- Xcode 15 with Command Line Tools (xcode-select --install)

- cmake --preset mac-release && cmake --build --preset mac-release

- Output: build/mac-release/ARLD.app — drag to Applications or run directly

## Linux (Ubuntu 22.04 / Fedora 38)

- sudo apt install build-essential ninja-build  (Ubuntu) or  sudo dnf install gcc-c++ ninja-build  (Fedora)

- cmake --preset linux-release && cmake --build --preset linux-release

- Output: build/linux-release/ARLD.AppImage — chmod +x and run

## Windows 10/11

- Visual Studio 2022 with Desktop development with C++ workload

- cmake --preset win-release && cmake --build --preset win-release

- Output: build/win-release/Release/ARLD.exe — run directly or use CPack to generate .msi

# Appendix C: Glossary

| Term | Definition |
| --- | --- |
| ARLD | Airshow Ramp Layout Designer — the application described in this charter. |
| CGAL | Computational Geometry Algorithms Library — open-source C++ library (LGPL) used for polygon clearance-zone computations. |
| CMake | Open-source build system generator used to produce native build files for Xcode, Ninja, and MSVC from a single CMakeLists.txt. |
| CoW | Certificate of Waiver — FAA authorization permitting airshow operations, specifying minimum separation distances. |
| CPack | CMake packaging tool used to generate platform-native installers (.dmg, .AppImage, .msi). |
| FOD | Foreign Object Debris — any object on an airfield surface that could damage aircraft or injure personnel. |
| Hot Ramp | A ramp area where engines are running or fueling is in progress; subject to enhanced clearance requirements. |
| ICAS | International Council of Air Shows — trade organization publishing airshow safety standards. |
| LGPL | GNU Lesser General Public License — permits linking without copyleft obligations when the library is dynamically linked. |
| PoC | Proof of Concept — the 10-week Phase 0 C++ application validating core technology choices. |
| Prop Arc | The swept circle of a propeller; defines minimum clearance radius for propeller-driven aircraft. |
| SaaS | Software as a Service — the Phase 4 cloud-hosted web application and subscription offering. |
| Silhouette | Top-down orthographic SVG vector outline of an aircraft rendered at true scale on the canvas. |
| Static Display | Aircraft on public display that are shut down and chocked; the most common ramp configuration. |
| vcpkg | Open-source C++ package manager (MIT) from Microsoft; manifest mode ensures reproducible dependency resolution. |
| Warbird | Vintage military aircraft, typically WWII-era; may have additional clearance requirements due to radial engine prop arcs. |

— End of Document —