AIRSHOW RAMP LAYOUT DESIGNER

Project Plan

Sprint-by-Sprint Delivery Schedule  |  All Phases  |  Version 1.0

| Document Title | ARLD Project Plan |
| --- | --- |
| Project | Airshow Ramp Layout Designer (ARLD) |
| Version | 1.0 |
| Prepared By | Program Management Office |
| Date | May 2026 |
| Sprint Cadence | 2 weeks per sprint |
| Phases Covered | Phase 0 (PoC) through Phase 4 (SaaS) |
| Classification | Confidential — Internal Use Only |

Version 1.0  |  May 2026  |  FOR INTERNAL USE ONLY

# 1. Introduction and Planning Framework

## 1.1  Purpose

This Project Plan translates the ARLD Project Charter v2.0, Functional Requirements Document v1.0, and Technical Requirements Document v1.0 into a sprint-by-sprint delivery schedule. Each sprint is two weeks in duration. Stories are sized in Fibonacci story points (1, 2, 3, 5, 8, 13). The plan covers all five phases: Phase 0 (C++ PoC), Phase 1 (Foundation), Phase 2 (Complete Desktop), Phase 3 (Desktop Launch), and Phase 4 (SaaS — pending separate approval).

## 1.2  Team Capacity and Velocity Assumptions

The core team for Phases 0–3 comprises 6.25 FTE. Nominal team velocity is established in Sprint 0-1 and refined over the first four sprints. The table below shows assumed capacity per phase:

| Phase | Active Roles | FTE | Target Velocity | Sprint Duration |
| --- | --- | --- | --- | --- |
| Phase 0 (Wks 1–10) | Lead C++ Eng, 1× C++ Eng, QA, Domain Consultant (pt) | 3.25 FTE | 28–32 pts/sprint | 2 weeks |
| Phase 1 (Mo 3–6) | Full team onboarded: +2× C++ Eng, UX, Data Curator, PM | 6.25 FTE | 42–48 pts/sprint | 2 weeks |
| Phase 2 (Mo 7–12) | Full team + UAT participants (external) | 6.25 FTE | 44–50 pts/sprint | 2 weeks |
| Phase 3 (Mo 13–14) | Full team; engineering winds down to maintenance mode | 5.0 FTE | 36–42 pts/sprint | 2 weeks |
| Phase 4 (separate) | New web/cloud team (TBD at Phase 4 kickoff) | TBD | TBD | 2 weeks |

## 1.3  Story Point Scale

| Points | Effort Level | Typical Work Description |
| --- | --- | --- |
| 1 | Trivial | Configuration change, copy edit, 1-line fix, documentation update |
| 2 | Small | Isolated bug fix, minor UI tweak, adding a single unit test, updating a JSON schema field |
| 3 | Medium-small | Self-contained feature with clear scope, e.g., implementing one export option, adding a library filter |
| 5 | Medium | Multi-file implementation with tests; e.g., a new clearance display type, Qt panel with signals/slots |
| 8 | Large | Cross-module work requiring design; e.g., CGAL Minkowski sum integration, PDF title block renderer |
| 13 | X-Large | Full sub-system; e.g., complete canvas LOD system, full violation override workflow end-to-end |

## 1.4  Definition of Done

A story is Done when ALL of the following are true:

- Code merged to main branch via reviewed pull request with no unresolved comments

- All new code covered by Catch2 unit tests; overall core/ coverage remains ≥ 80%

- CI pipeline passes: build (all 3 platforms), lint (clang-tidy), tests, license-check

- Acceptance criteria in this plan verified by QA Engineer or Domain Consultant as noted

- Any new user-visible string wrapped in tr() and added to the .ts translation file

- Architecture Decision Record updated if the story introduces a new design pattern or library

PHASE 0 — C++ Proof of Concept Weeks 1–10 ¦ Sprints 0-1 through 0-5 ¦ Open-source-only desktop prototype on macOS, Linux, and Windows

Phase 0 is a strict 10-week time-box. Its sole purpose is to validate the technology stack (Qt 6, CGAL, CMake/vcpkg, stb_image_write, nlohmann/json) before any production investment is made. No user accounts, no cloud connectivity, no production polish. Team size is intentionally lean.

| Sprint 0-1 | Dates Weeks 1–2 | Points 30 | Sprint Goal: Repository scaffold, CI green on all 3 platforms, CMake + vcpkg baseline |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 0-1-1 | Set up Git repository with Apache 2.0 LICENSE, README, .gitignore, and CONTRIBUTING guide | TRD-BUILD-001 | Lead C++ Eng | 2 | Repo visible to team; README renders correctly on GitHub |
| 0-1-2 | Author CMakeLists.txt with four-module add_subdirectory structure (core, ui, export, app) | TRD-ARCH-001 TRD-BUILD-001 | Lead C++ Eng | 5 | cmake --preset linux-debug produces build directory with no errors |
| 0-1-3 | Add vcpkg.json manifest pinning Qt 6.7, CGAL 5.6, nlohmann/json 3.11, Catch2 3.x | TRD-BUILD-002 | Lead C++ Eng | 3 | vcpkg install completes on all 3 platforms from clean clone |
| 0-1-4 | Create CMakePresets.json with all 6 presets (mac/linux/win × debug/release) | TRD-BUILD-001 FRD PLAT-003 | Lead C++ Eng | 3 | Each preset produces a separate binaryDir; cmake --preset mac-release succeeds on macOS CI |
| 0-1-5 | Configure GitHub Actions matrix: macos-14, ubuntu-22.04, windows-2022; build + CTest | TRD-BUILD-004 | Lead C++ Eng | 5 | All 3 CI runners show green on a Hello World Qt application |
| 0-1-6 | Add SPDX license-checker CI job; confirm no GPL in initial dependency graph | TRD-BUILD-005 TRD-SEC-040 | QA Eng | 5 | license-check job passes; LICENSES.txt generated with all SPDX identifiers |
| 0-1-7 | Stub out arld/core/Config.h with clearance distance constants (FAA CoW defaults) | TRD-ARCH-004 FRD CLR-006–011 | Lead C++ Eng | 3 | Config.h compiles in headless test; constants match charter §6.3 values |
| 0-1-8 | Write first Catch2 smoke test: instantiate and destroy a Layout object; CTest passes | TRD-TEST-001 | QA Eng | 2 | ctest --preset linux-debug shows 1/1 tests passed |

| Sprint 0-2 | Dates Weeks 3–4 | Points 34 | Sprint Goal: Qt canvas prototype: ramp boundary polygon, pan, zoom, snap grid |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 0-2-1 | Create RampScene : public QGraphicsScene and RampView : public QGraphicsView skeleton classes | TRD-CANVAS-001 TRD-ARCH-002 | Lead C++ Eng | 3 | Empty Qt window opens on all 3 platforms; scene attached to view |
| 0-2-2 | Implement logical coordinate system: 1 unit = 1 ft; QGraphicsView transform maps to screen pixels at zoom | TRD-CANVAS-001 | Lead C++ Eng | 5 | A 100 ft × 100 ft boundary polygon fills ~1 inch on screen at 1:1200 scale |
| 0-2-3 | Implement pan via click-drag (mouse) and two-finger drag (trackpad) | FRD CAN-010 | Lead C++ Eng | 3 | Canvas pans smoothly; no jitter on 1080p display |
| 0-2-4 | Implement zoom via scroll wheel and +/- shortcuts; anchor to cursor position (AnchorUnderMouse) | TRD-CANVAS-002 FRD CAN-011 | C++ Eng #2 | 5 | Zoom range 1:200 to 1:5000; cursor position stays fixed during zoom |
| 0-2-5 | Implement RampBoundaryItem: polygon draw by clicking points; close on double-click | FRD CAN-001 FRD CAN-005 | C++ Eng #2 | 5 | User can define a 6-point boundary; polygon styled with distinct outline |
| 0-2-6 | Implement vertex drag editing on RampBoundaryItem | FRD CAN-002 | C++ Eng #2 | 3 | Dragging any vertex updates polygon in real time; no gaps or self-intersections |
| 0-2-7 | Add ScaleBarItem: dynamic scale bar updates on every zoom change | FRD CAN-020 TRD-CANVAS-001 | Lead C++ Eng | 3 | Scale bar shows correct footage at 1:500, 1:1000, 1:2000 |
| 0-2-8 | Add snap-to-grid with default 5 ft spacing; configurable via Config.h constant | FRD PLAC-003 | C++ Eng #2 | 3 | Aircraft snaps to 5 ft grid; snap can be disabled via Shift key |
| 0-2-9 | Define ICommand interface with execute(), undo(), describe(); wire Ctrl+Z / Ctrl+Y | TRD-ARCH-005 FRD CAN-030–032 | Lead C++ Eng | 5 | Undo/redo of boundary draw cycles correctly 100 levels deep; keyboard shortcuts work on all platforms |

| Sprint 0-3 | Dates Weeks 5–6 | Points 36 | Sprint Goal: 20-aircraft library with scaled SVG silhouettes; drag-and-drop placement |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 0-3-1 | Define AircraftLibraryEntry JSON schema; create 20 seed entries covering all major categories (warbird, military, static, aerobatic, rotary, ultralight, heritage) | TRD-DATA-003 FRD LIB-001 FRD LIB-004 | Data Curator | 8 | 20 JSON files pass schema validation in CI; all required fields present and in range |
| 0-3-2 | Source or create SVG silhouettes for all 20 seed aircraft; scale to published wingspan | FRD LIB-005 | Data Curator | 8 | Each SVG renders at correct wingspan when placed at 1:1000 scale; no copyright-protected artwork |
| 0-3-3 | Implement AircraftLibraryParser: load JSON files from arld/data/library/; cache AircraftLibraryEntry structs | TRD-DATA-003 TRD-ARCH-003 | Lead C++ Eng | 5 | Library loads in < 500 ms; headless Catch2 test verifies all 20 entries parsed without error |
| 0-3-4 | Create AircraftItem : QGraphicsItemGroup containing SilhouetteItem : QGraphicsSvgItem | TRD-CANVAS-007 FRD PLAC-002 | C++ Eng #2 | 5 | Dropped aircraft renders SVG silhouette at correct scale; bounding rect matches wingspan × length |
| 0-3-5 | Implement drag-from-library-panel drop-onto-canvas placement | FRD PLAC-001 | C++ Eng #2 | 5 | User can drag any of 20 types onto canvas; placement recorded in undo stack |
| 0-3-6 | Implement 1-degree rotation handle on AircraftItem; snap-to-45 when within 3° of multiple | FRD PLAC-010 TRD-CANVAS-007 | Lead C++ Eng | 5 | Aircraft rotates in 1° steps; snaps to 0/45/90/135/180/225/270/315 when near boundary |
| 0-3-7 | Assign default display type STATIC_DISPLAY on placement; wire PLAC-020 enum to AircraftItem | FRD PLAC-020 FRD PLAC-022 | C++ Eng #2 | 3 | Newly placed aircraft has display_type = STATIC_DISPLAY in its placement record |

| Sprint 0-4 | Dates Weeks 7–8 | Points 35 | Sprint Goal: CGAL clearance zones, real-time violation detection and highlighting |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 0-4-1 | Define GeomTypes.h with CGAL kernel and required type aliases (Kernel, Point2, Polygon2, PolySet, FT) | TRD-GEOM-001 TRD-ARCH-003 | Lead C++ Eng | 3 | GeomTypes.h compiles in headless core/ test with no Qt dependency |
| 0-4-2 | Implement ClearanceEngine::computeEnvelope(): Minkowski sum of aircraft convex hull and clearance circle using CGAL::minkowski_sum_2() | TRD-GEOM-001 TRD-GEOM-002 | Lead C++ Eng | 13 | Catch2 test: envelope for P-51D at Static Display = hull + 25 ft circle; shape is correct polygon |
| 0-4-3 | Implement propeller arc clearance zones as 36-gon sector polygons (360° tractor / 180° pusher) | TRD-GEOM-004 FRD CLR-002 | Lead C++ Eng | 8 | Tractor P-51D arc covers full 360°; pusher Extra 330 arc covers rear hemisphere only |
| 0-4-4 | Implement rotor disc clearance zones as circles for rotary-wing entries | TRD-GEOM-005 FRD CLR-003 | C++ Eng #2 | 3 | UH-1 rotor disc renders as 48 ft diameter circle overlay |
| 0-4-5 | Implement ClearanceEngine::detectViolations(): CGAL::do_intersect() on all pairs; CGAL::squared_distance() for gap measurement | TRD-GEOM-003 FRD CLR-020 | Lead C++ Eng | 8 | Catch2: two P-51Ds placed 20 ft wingtip-to-wingtip → 1 violation; moved to 30 ft → 0 violations |
| 0-4-6 | Implement ClearanceZoneItem: three-color overlay (green ≥110%, yellow 100–110%, red <100%) | FRD CLR-021 TRD-EXP-003 | C++ Eng #2 | 5 | Zone colours switch in real time as aircraft are dragged; colour thresholds match spec |
| 0-4-7 | Wire violationsChanged(QList<Violation>) signal; connect to stub ViolationsPanel label showing count | TRD-CANVAS-008 FRD CLR-020 | C++ Eng #2 | 3 | Violation count badge updates within one frame of any aircraft move |
| 0-4-8 | Implement spatial index (QRectF R-tree) to prune non-intersecting pairs before CGAL check | TRD-GEOM-009 | Lead C++ Eng | 5 | bench_geom benchmark: 200 aircraft full re-evaluation completes < 50 ms on CI runner (ubuntu-22.04) |
| 0-4-9 | Write ClearanceEngineTests fixture covering the 6 mandatory scenarios (TRD-TEST-002) | TRD-TEST-002 FRD CLR-026 | QA Eng | 5 | All 6 test cases pass on all 3 CI platforms; coverage of clearance engine ≥ 80% |

| Sprint 0-5 | Dates Weeks 9–10 | Points 32 | Sprint Goal: SVG export, JSON project save/load, PoC acceptance gate |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 0-5-1 | Implement SvgExporter using QSvgGenerator; viewBox = ramp boundary + 5% margin; include all visible items | TRD-EXP-001 FRD EXP-001–003 | Lead C++ Eng | 8 | Exported SVG opens in Inkscape and browser; aircraft silhouettes, boundary, clearance zones, scale bar all present |
| 0-5-2 | Implement JSON project save: serialize Layout to .arld file (§5.1 schema); placement_id = UUID v4 | TRD-DATA-001 TRD-DATA-002 FRD PROJ-001 | Lead C++ Eng | 8 | Saved file is valid JSON; passes arld-project.schema.json validation |
| 0-5-3 | Implement JSON project load: parse .arld; reconstruct AircraftItems and clearance zones; round-trip test | TRD-TEST-003 FRD PROJ-003 | Lead C++ Eng | 5 | Round-trip Catch2 test: save 15-aircraft layout → reload → all positions, headings, display types identical |
| 0-5-4 | Implement NorthArrowItem; add Fit-to-Window toolbar button | FRD CAN-013 FRD CAN-021 | C++ Eng #2 | 3 | North arrow visible at all zoom levels; Fit to Window frames the ramp boundary with 5% padding |
| 0-5-5 | Implement Hot Ramp no-smoking radius (QGraphicsEllipseItem, 100 ft); boundary breach flag | TRD-GEOM-007 FRD CLR-010 | C++ Eng #2 | 3 | Hot Ramp aircraft shows orange circle; boundary-breach warning fires when circle extends outside ramp polygon |
| 0-5-6 | Run bench_canvas CI benchmark: 200 AircraftItems, 300 pan/zoom frames, assert mean < 16.7 ms | TRD-TEST-005 TRD-CANVAS-003 | QA Eng | 3 | Benchmark passes on all 3 CI runners; JSON artifact uploaded to GitHub Actions |
| 0-5-7 | Execute PoC acceptance test with Aviation Domain Consultant (10-aircraft layout ≤ 20 min) | TRD-TEST-010 Charter §5.4 | QA Eng + Domain | 5 | Domain expert completes layout in ≤ 20 min unassisted; sign-off report filed |
| 0-5-8 | PoC gate review: confirm all 6 Charter §5.4 criteria; obtain sign-off; tag v0.1.0-poc | Charter §5.4 | PM | 2 | All criteria verified; tag present in repo; Phase 1 kickoff meeting scheduled |

⭐ Phase 0 Gate — PoC Sign-Off (End of Week 10) - CI green (build + tests + license-check) on macos-14, ubuntu-22.04, windows-2022 - 20 aircraft types in library with correct scaled silhouettes - 15-aircraft layout: create → save → reload → SVG export with no data loss (round-trip test) - 5 violation scenarios correctly detected per ClearanceEngineTests fixture - Domain expert completes 10-aircraft layout in < 20 min unassisted - No GPL-licensed code in distributable binaries (license-check CI passes) - v0.1.0-poc tag created; PoC Sign-off Report filed with PM

PHASE 1 — Foundation Months 3–6 ¦ Sprints 1-1 through 1-6 ¦ Production-quality C++ desktop; full aircraft library; all display types

| Sprint 1-1 | Dates Month 3, Wk 1–2 | Points 46 | Sprint Goal: PoC-to-production refactor; installer scaffolding; full team onboards |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 1-1-1 | Refactor PoC code to enforce four-layer module boundaries; add static analysis (clang-tidy) CI job with baseline | TRD-ARCH-001 TRD-BUILD-007 | Lead C++ Eng | 8 | clang-tidy CI job passes; zero cross-layer includes detected by include-what-you-use |
| 1-1-2 | Set up CPack configurations for .dmg (macOS), .AppImage + .deb (Linux), .msi (Windows); smoke-install on each platform | FRD PLAT-030–033 TRD-BUILD-008 | Lead C++ Eng | 8 | Installable packages generated; app launches from installed location on all 3 platforms; no admin rights required |
| 1-1-3 | Implement UnitConverter singleton: ft↔m; wire PROJ-020 unit toggle; all display values call toDisplay() | TRD-A11Y-011 FRD PROJ-020–022 | C++ Eng #2 | 5 | Switching metric/imperial updates scale bar, violation distances, and all panels without data loss |
| 1-1-4 | Implement auto-save every 60 s to QStandardPaths::CacheLocation/{uuid}.arld.autosave | TRD-DATA-005 FRD PROJ-004 | C++ Eng #2 | 3 | Auto-save file appears within 65 s; file is valid JSON; deleted on clean exit |
| 1-1-5 | Implement crash-recovery dialog on launch: detect .autosave file; offer restore | FRD PROJ-005 | C++ Eng #2 | 3 | Simulated unclean exit → relaunch → dialog appears; restoring loads correct layout |
| 1-1-6 | Implement IExporter strategy: SvgExporter, PdfExporter (stub), PngExporter (stub), JpegExporter (stub), BatchExporter | TRD-ARCH-007 FRD FR-EXPORT | Lead C++ Eng | 5 | Each exporter class compiles; BatchExporter calls all four; stubs produce empty files |
| 1-1-7 | UX Designer: deliver wireframes for main window, library browser, violations panel, properties panel | FRD 2.2 User Roles | UX Designer | 5 | Figma file shared; wireframes reviewed and signed off by PM and Lead Eng |
| 1-1-8 | Data Curator: expand aircraft library to 50 entries; validate all dimensional data against 3 sources | FRD LIB-002 TRD-DATA-003 | Data Curator | 8 | 50 entries pass CI schema validation; each entry has data_source and verified_date fields populated |

| Sprint 1-2 | Dates Month 3, Wk 3–4 | Points 44 | Sprint Goal: Violations panel, clearance rule configuration, display type assignment UI |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 1-2-1 | Implement full ViolationsPanel: list of active violations with aircraft IDs, type, measured gap, required minimum, severity badge | FRD CLR-022 FRD CLR-024 | C++ Eng #2 | 8 | Panel shows correct violation count; clicking a row centres view on the offending aircraft pair |
| 1-2-2 | Implement ClearanceRuleSet JSON schema and loader; FAA CoW defaults pre-loaded from arld/data/rules/faa_cow.json | TRD-ARCH-006 FRD CLR-030 FRD CLR-034 | Lead C++ Eng | 5 | Schema validation rejects malformed rule files; FAA CoW distances match Charter §6.3 values |
| 1-2-3 | Implement show-specific clearance rule override dialog (Show Director role); rules saved in .arld file | FRD CLR-031 FRD CLR-032 FRD CLR-033 | C++ Eng #2 | 5 | User can change static_display_wingtip from 25 to 30 ft; violation thresholds update immediately; value < 0 rejected |
| 1-2-4 | Implement ICAS Standard clearance rule template; add template picker to rule dialog | FRD CLR-034 | C++ Eng #2 | 3 | ICAS template loads; its distances differ from FAA CoW defaults where ICAS specifies stricter values |
| 1-2-5 | Implement display type assignment dropdown on AircraftItem properties panel; all 7 types wired | FRD PLAC-020 FRD PLAC-021 FRD PLAC-023 | C++ Eng #2 | 5 | Changing display type immediately recalculates clearance zone; visual badge updates on canvas |
| 1-2-6 | Implement clearance override dialog: justification text field (min 20 chars); store in overrides[] array | FRD CLR-040 FRD CLR-041 FRD CLR-042 TRD-DATA-006 | Lead C++ Eng | 8 | Override persists in .arld file with justification, username, and ISO-8601 timestamp; orange outline renders |
| 1-2-7 | Add tail number, owner, fuel type, hazmat metadata fields to AircraftItem properties panel | FRD PLAC-030 FRD PLAC-031 | UX Designer + C++ Eng #2 | 5 | Hazmat flag displays skull icon on canvas; metadata round-trips through .arld file |
| 1-2-8 | Write schema migration skeleton: schema_version bump function; Catch2 round-trip migration test | TRD-DATA-001 | Lead C++ Eng | 3 | test_schema_migration: v0 file loads in v1 app without error; re-saved as v1 |

| Sprint 1-3 | Dates Month 4, Wk 1–2 | Points 47 | Sprint Goal: Library browser UI; custom aircraft entries; heading controls |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 1-3-1 | Implement library browser panel: text search filtered by manufacturer/model; category filter dropdown | FRD LIB-010 FRD LIB-011 | UX Designer + C++ Eng #2 | 8 | Typing 'P-51' filters to Mustang variants; category filter shows only Warbirds when selected |
| 1-3-2 | Add thumbnail silhouette preview, wingspan, and length to each library browser result row | FRD LIB-012 | C++ Eng #2 | 5 | Each row shows scaled SVG thumbnail (48×48), wingspan, and length in current unit system |
| 1-3-3 | Implement custom aircraft entry dialog: all required dimensional fields; validate ranges; save to user library | FRD LIB-020 FRD LIB-021 | C++ Eng #2 | 8 | User creates custom entry with uploaded SVG; entry appears in library browser; used in layout |
| 1-3-4 | Implement SVG sanitization for user-uploaded silhouettes: strip XXE, <script>, <foreignObject> | TRD-SEC-004 | Lead C++ Eng | 5 | Catch2 test: malicious SVG with <script> tag → sanitizer strips it; safe SVG passes unchanged |
| 1-3-5 | Implement exact heading input field (0–359°) on properties panel; snap-to-runway-heading control with user-defined heading | FRD PLAC-012 FRD PLAC-013 | C++ Eng #2 | 5 | Typing '270' rotates aircraft to west; snap-to-runway aligns all selected aircraft to entered heading |
| 1-3-6 | Expand aircraft library to 75 entries; all entries pass CI schema validation | FRD LIB-002 TRD-TEST-007 | Data Curator | 8 | 75 entries in CI; TRD-TEST-007 schema validation step passes; no duplicate IDs |
| 1-3-7 | Add coordinate grid overlay (GridOverlayItem); configurable spacing (25/50/100 ft); togglable | TRD-CANVAS-005 FRD CAN-022 | C++ Eng #2 | 5 | Grid spacing selector works; grid recomputes on zoom change; toggle shows/hides instantly |
| 1-3-8 | Implement Fit-to-Window and recently-opened projects list (last 10) | FRD CAN-013 FRD PROJ-006 | C++ Eng #2 | 3 | File menu shows last 10 projects; Fit-to-Window frames ramp with 5% margin |

| Sprint 1-4 | Dates Month 4, Wk 3–4 | Points 44 | Sprint Goal: Tail-dragger tail-swing, extended gear, accessibility foundation |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 1-4-1 | Implement tail-dragger tail-swing arc: precompute swept polygon from min_turn_radius_ft at library load; add to clearance envelope | TRD-GEOM-006 FRD CLR-004 | Lead C++ Eng | 8 | Stearman PT-17 tail-swing arc visible on canvas; overlapping tail-swing triggers violation |
| 1-4-2 | Implement extended/retracted gear clearance variants; gear state selector on properties panel | FRD CLR-005 | Lead C++ Eng | 5 | P-47 with gear extended shows larger clearance envelope than gear retracted; zone updates on toggle |
| 1-4-3 | Implement Taxi-Only corridor (50 ft lane) and Military Static standoff (50 ft perimeter) zone renderers | FRD CLR-008 FRD CLR-009 | C++ Eng #2 | 5 | Taxi-Only aircraft shows 50 ft corridor along rotation axis; Military Static shows 50 ft perimeter |
| 1-4-4 | Implement Media/Photo Platform crush-barrier overlay (QGraphicsPolygonItem, configurable shape) | FRD CLR-011 | C++ Eng #2 | 3 | Media platform aircraft shows barrier polygon; overlay exports in SVG and PNG |
| 1-4-5 | Implement Ramp Show Aircraft 200 ft crowd-line clearance zone | FRD CLR-011 | C++ Eng #2 | 3 | Ramp Show aircraft shows 200 ft zone; violation fires if another aircraft enters it |
| 1-4-6 | Enable QAccessible on AircraftItem and RampBoundaryItem; set accessibleName to tail number + display type | TRD-A11Y-003 | Lead C++ Eng | 5 | macOS VoiceOver reads tail number and display type when AircraftItem is focused |
| 1-4-7 | Wrap all user-visible strings in tr(); configure lupdate CI step; create en.ts baseline | TRD-A11Y-010 | C++ Eng #2 | 5 | lupdate runs in CI; zero untranslated strings in UI code; en.ts committed |
| 1-4-8 | Keyboard navigation: all toolbar controls, panels, dropdowns accessible via Tab; focus order follows visual layout | TRD-A11Y-001 | UX Designer + C++ Eng #2 | 5 | Full UI navigable by keyboard; Tab order matches left-to-right, top-to-bottom reading order |
| 1-4-9 | Deliver accessibility audit using axe or Qt Accessibility Inspector; document baseline issues | TRD-A11Y-002 | QA Eng | 5 | Audit report filed; all WCAG 2.1 AA critical issues resolved; colour-vision pattern fills added to zone overlays |

| Sprint 1-5 | Dates Month 5, Wk 1–2 | Points 45 | Sprint Goal: PDF export (libharu), satellite underlay, violation export report |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 1-5-1 | Implement PdfExporter using libharu 2.4; support Letter, Tabloid, ANSI-C, ANSI-D, ANSI-E, ANSI-E1 paper sizes | TRD-EXP-010 FRD EXP-010–011 | Lead C++ Eng | 13 | PDF opens in Adobe Acrobat; correct paper size selected; all visible canvas layers present |
| 1-5-2 | Embed Inter font subset (SIL OFL) in PDF output via HPDF_LoadTTFontFromFile; add title block at bottom 1.5 inches | TRD-EXP-011 TRD-EXP-013 FRD EXP-012–013 | Lead C++ Eng | 8 | PDF title block contains Show Name, Date, Venue, Version, Export Date; font is embedded (verify in Acrobat) |
| 1-5-3 | Implement ICC-aware CMYK color conversion for PDF using bundled sRGB.icc; add /OutputIntents to PDF | TRD-EXP-012 FRD EXP-016–017 | Lead C++ Eng | 5 | PDF/X-1a compliance check in Preflight passes; no unembedded fonts; CMYK colors correct |
| 1-5-4 | Add QR code in PDF title block (checksum of .arld file) using libqrencode (LGPL) | TRD-EXP-013 | C++ Eng #2 | 3 | QR code scans to SHA-256 hash string of the saved .arld project file |
| 1-5-5 | Add display type legend to PDF footer band; portrait/landscape orientation selector | FRD EXP-014 FRD EXP-018 | C++ Eng #2 | 3 | Legend identifies all 7 display types with colour swatches; orientation selector works for all paper sizes |
| 1-5-6 | Implement satellite underlay: user imports image file; QImageReader loads async on worker thread; opacity slider 0–100% | TRD-CANVAS-006 FRD CAN-023 | C++ Eng #2 | 8 | Loading a 10 MB JPEG does not block UI; placeholder shows; opacity slider updates rendering in real time |
| 1-5-7 | Implement Export Violations Report: PDF/CSV listing all violations with gap, minimum, severity; override section | FRD CLR-025 FRD CLR-043 | C++ Eng #2 | 5 | Violations report PDF lists all active violations and overrides; override justification text included |

| Sprint 1-6 | Dates Month 6, Wk 1–2 | Points 43 | Sprint Goal: PNG/JPEG export, project save polish, alpha release to 10 beta users |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 1-6-1 | Implement PngExporter using stb_image_write; DPI presets {72,96,150,300,600}; transparent + white background | TRD-EXP-020 FRD EXP-020–023 | Lead C++ Eng | 5 | 300 DPI PNG of reference layout matches golden file (pHash ≤ 8); transparent background verified |
| 1-6-2 | Implement JpegExporter using stb_image_write; quality 60–100% in 5% steps; max dimension cap 32767 px with warning | TRD-EXP-021 TRD-EXP-022 FRD EXP-030–033 | Lead C++ Eng | 5 | JPEG at 90% quality of reference layout matches golden file (pHash ≤ 8); cap warning fires correctly |
| 1-6-3 | Store golden reference files in arld/tests/golden/ via Git LFS; CI export test compares all 4 format outputs | TRD-TEST-004 | QA Eng | 5 | CI export test passes on all 3 platforms; pHash differences < 8 for each format |
| 1-6-4 | Implement .arld file versioning: schema_version=1; migration from v0 PoC files tested | TRD-DATA-001 FRD PROJ-002 | Lead C++ Eng | 3 | Opening a v0 PoC file offers upgrade; re-saved file has schema_version=1 and all data intact |
| 1-6-5 | Implement recently-used files list; project metadata dialog (show name, date, venue, units) | FRD PROJ-006 | C++ Eng #2 | 3 | File > Recent shows last 10 paths; metadata dialog fields persist in .arld file |
| 1-6-6 | Build and distribute alpha installers (.dmg, .AppImage, .msi) to 10 beta users; collect structured feedback | Charter §9 Phase 1 Milestone | PM + QA Eng | 5 | 10 beta users receive installers; feedback form completed by at least 8 |
| 1-6-7 | Triage alpha feedback; create bug backlog; update risk register | Charter Risk Register | PM | 3 | All P1 bugs filed as GitHub issues; risk register updated; sprint retrospective completed |
| 1-6-8 | Code coverage report: core/ and export/ ≥ 80%; upload to Codecov; CI coverage gate active | TRD-BUILD-006 | QA Eng | 5 | Codecov shows ≥ 80% for both modules; CI fails if coverage drops below threshold |
| 1-6-9 | Locale-aware decimal parsing: QLocale::system() for input; always serialise JSON with '.' separator | TRD-A11Y-012 | C++ Eng #2 | 3 | French locale: '25,0' accepted in input; saved JSON shows 25.0; round-trip verified |

⭐ Phase 1 Gate — Alpha Sign-Off (End of Month 6) - Installable alpha on all three platforms (macOS .dmg, Linux .AppImage, Windows .msi) - 75+ aircraft types in library; all entries pass CI schema validation - All 7 display types implemented with correct clearance zone logic - Violation override workflow functional with persisted justifications - PDF, PNG, and JPEG export functional; golden-file CI test passing - Satellite underlay loads asynchronously; no UI thread blocking - Code coverage core/ and export/ ≥ 80%; clang-tidy CI job passing - 10 beta users have received installers; structured feedback collected

PHASE 2 — Complete Desktop Product Months 7–12 ¦ Sprints 2-1 through 2-6 ¦ Full library, batch export, layout versioning, UAT

| Sprint 2-1 | Dates Month 7, Wk 1–2 | Points 50 | Sprint Goal: Complete 150-type aircraft library; batch export; SVG named layers |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 2-1-1 | Expand aircraft library to 150 entries; all dimensional data verified against ≥ 3 sources; CI schema validation | FRD LIB-003 TRD-TEST-007 | Data Curator | 13 | 150 entries in CI; zero schema validation failures; each entry has data_source and verified_date |
| 2-1-2 | Implement BatchExporter: produce all 4 formats (SVG, PDF, PNG, JPEG) with one action using last-saved settings | FRD EXP-040 FRD EXP-041 | Lead C++ Eng | 5 | Single 'Export All' button produces 4 files in output folder; no per-format dialogs shown |
| 2-1-3 | Add named SVG layers (<g id='...'> with inkscape:label) for each canvas layer; layer visibility honoured at export | TRD-EXP-002 FRD EXP-004 FRD EXP-005 | Lead C++ Eng | 5 | SVG opens in Inkscape with named layers; toggling a layer off then exporting omits it |
| 2-1-4 | Add scale bar overlay option to PNG export; implement named export configuration save/load | FRD EXP-023 FRD EXP-042 | C++ Eng #2 | 3 | PNG with scale bar option shows bar in output; saved config restores all settings on next export |
| 2-1-5 | Implement library browser: sort by name, wingspan, length; placement count badge | FRD LIB-013 FRD LIB-014 | C++ Eng #2 | 3 | Clicking 'Wingspan' column header sorts ascending/descending; count badge shows 3 for a type placed 3 times |
| 2-1-6 | Implement CSV metadata manifest export alongside diagram export | FRD PLAC-034 | C++ Eng #2 | 3 | CSV contains tail number, owner, fuel type, hazmat, arrival/departure for all placed aircraft |
| 2-1-7 | Implement multi-select and group move (Shift+click or drag lasso) | FRD PLAC-005 | C++ Eng #2 | 5 | Lasso selects multiple aircraft; dragging group moves all; undo reverts all positions together |
| 2-1-8 | Implement community entry submission portal (dialog → opens GitHub issue template in browser) | FRD LIB-023 | C++ Eng #2 | 3 | Button in library browser opens pre-filled GitHub issue with user-entered dimensions; requires internet |
| 2-1-9 | Performance regression: run bench_canvas and bench_geom; assert budgets still met with 150-type library | TRD-PERF-001 TRD-PERF-002 | QA Eng | 5 | Both benchmarks pass; cold-start ≤ 4 s; library load ≤ 500 ms verified |
| 2-1-10 | Export performance tests: SVG ≤ 3 s, PDF ≤ 8 s, PNG ≤ 6 s, JPEG ≤ 5 s (200-aircraft ANSI-D canvas) | TRD-PERF-003–006 | QA Eng | 5 | All 4 export benchmarks pass on ubuntu-22.04 CI runner; results committed as JSON artifacts |

| Sprint 2-2 | Dates Month 7, Wk 3–4 | Points 44 | Sprint Goal: Layout versioning, change-delta view, minimap, geo-referenced tile underlay |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 2-2-1 | Implement named layout snapshots (versions[]): save, list, switch between versions within one .arld file | FRD PROJ-010 FRD PROJ-011 | Lead C++ Eng | 8 | User saves 'Version A' and 'Version B'; switching reloads correct aircraft positions and counts |
| 2-2-2 | Implement visual change-delta view: highlight added (green), removed (red), moved (amber) aircraft between two selected versions | FRD PROJ-012 | Lead C++ Eng | 8 | Delta view correctly identifies 3 moved, 1 added, 1 removed aircraft in a test scenario |
| 2-2-3 | Implement version export as standalone .arld file | FRD PROJ-013 | C++ Eng #2 | 2 | Exported standalone file opens independently; version metadata preserved |
| 2-2-4 | Implement minimap overview panel: scaled-down ramp view with viewport rectangle indicator | FRD CAN-014 | C++ Eng #2 | 5 | Minimap updates as user pans; clicking minimap centres main view on that point |
| 2-2-5 | Implement opt-in geo-referenced tile streaming underlay (Mapbox/Google Static Maps); opacity slider | FRD CAN-024 TRD-SEC-001 | C++ Eng #2 | 8 | Satellite tiles load when user provides API key in settings; HTTPS only; no request sent without user action |
| 2-2-6 | Add undo/redo history panel (last 20 actions with labels); accessible via View menu | FRD CAN-033 | C++ Eng #2 | 5 | History panel lists 20 most recent actions by name; clicking an entry undoes to that point |
| 2-2-7 | KML/GeoJSON boundary import; convert to logical-ft coordinate polygon | FRD CAN-004 | Lead C++ Eng | 5 | Importing a sample airport KML file draws the apron boundary correctly at scale |
| 2-2-8 | Update release packaging workflow: tag-triggered CPack builds; attach to GitHub Release; publish community edition | TRD-BUILD-008 FRD PLAT-034 | Lead C++ Eng + QA Eng | 3 | A test v0.2.0-beta tag triggers packaging CI; all 4 artefacts attach to draft GitHub Release |

| Sprint 2-3 | Dates Month 8–9, Wk 1–2 | Points 47 | Sprint Goal: Opt-in library update service, LOD rendering, beta release |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 2-3-1 | Implement opt-in library update check: HTTPS fetch of library_manifest.json; SHA-256 hash comparison; incremental download of changed entries only | FRD LIB-030 FRD LIB-031 TRD-SEC-002 | Lead C++ Eng | 8 | Update check fires only on user action; TLS cert validated; user-customised entries not overwritten without confirmation |
| 2-3-2 | Implement LOD rendering: at zoom < 1:2000, render AircraftItems as simplified bounding rectangles | TRD-CANVAS-004 | Lead C++ Eng | 5 | 200-aircraft layout at 1:3000 zoom maintains 60 fps on minimum hardware (verified by bench_canvas) |
| 2-3-3 | Implement arrival/departure time fields; fuel type auto-trigger of no-smoking overlay in Hot Ramp mode | FRD PLAC-030 FRD PLAC-032 | C++ Eng #2 | 3 | JET-A aircraft placed in Hot Ramp automatically shows 100 ft no-smoking circle; AVGAS does not |
| 2-3-4 | Implement aircraft label toggle (tail number / call sign) per aircraft on canvas | FRD PLAC-033 | C++ Eng #2 | 2 | Right-click menu toggles label; label state persists in .arld file |
| 2-3-5 | Implement locale-based decimal separator in all numeric inputs; lupdate CI confirms no missing strings | TRD-A11Y-012 TRD-A11Y-010 | C++ Eng #2 | 3 | German locale: 25,0 accepted; JSON always serialises as 25.0; lupdate CI green |
| 2-3-6 | Implement WCAG contrast audit tooling in CI; add pattern fills as supplement to colour coding for CVD users | TRD-A11Y-002 | UX Designer + QA Eng | 5 | Automated contrast check runs in CI; clearance zones have pattern fills (dots/stripes) in addition to colour |
| 2-3-7 | Performance benchmark suite: add TRD-PERF-007–010 timed tests; cold start, project open, library load, auto-save | TRD-PERF-007–010 | QA Eng | 5 | All 10 TRD-PERF budgets pass on all 3 CI platforms; trend chart enabled in CI |
| 2-3-8 | Build and distribute beta release to 25 users via GitHub Releases; set up structured NPS survey | Charter Phase 2 Beta | PM | 3 | Beta release tag created; 25 users notified; NPS survey link included in release notes |
| 2-3-9 | Open-source license compliance review mid-point check; update LICENSES.txt and NOTICES.txt | TRD-SEC-040 TRD-SEC-042 FRD PLAT-042 | Lead C++ Eng + Legal | 5 | Legal confirms all dependencies in allowlist; NOTICES.txt generated at build time; included in About dialog |
| 2-3-10 | Security review: nlohmann/json SAX parser depth/length limits in place; network code compile-time flags verified | TRD-SEC-003 TRD-SEC-001 | Lead C++ Eng + QA Eng | 5 | Catch2 test: .arld file with nesting depth > 32 → rejected with error; network flag disabled in headless build |

| Sprint 2-4 | Dates Month 9–10, Wk 3–4 | Points 44 | Sprint Goal: UAT event 1, bug fixes, snap-to-runway and group move polish |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 2-4-1 | Conduct UAT session at Airshow Event 1 with production ramp data (30-aircraft layout scenario); screen-capture all sessions | TRD-TEST-011 | QA Eng + Domain | 8 | Task completion rate recorded; session video archived; all P1 bugs logged |
| 2-4-2 | Triage UAT Event 1 bugs; fix all Priority 1 issues before next UAT | Charter UAT | Lead C++ Eng + C++ Eng #2 | 8 | Zero open P1 bugs from UAT Event 1; regression tests added for each fix |
| 2-4-3 | Polish snap-to-runway heading: multi-select + snap aligns all selected aircraft to primary heading | FRD PLAC-013 | C++ Eng #2 | 3 | Selecting 5 aircraft → snap-to-runway rotates all to same heading; undo restores all original headings |
| 2-4-4 | Polish group move: lasso selection, arrow-key nudge (1 ft per press, 5 ft with Shift) | FRD PLAC-005 | C++ Eng #2 | 3 | Nudge moves all selected aircraft by 1 ft; Shift+nudge moves 5 ft; undo restores all |
| 2-4-5 | Implement Export Violations Report PDF: structured table, override justification section, QR code | FRD CLR-025 FRD CLR-043 | Lead C++ Eng | 5 | Violations PDF renders all active violations and overrides; QR links to project checksum |
| 2-4-6 | Add violation count badge to application title bar and taskbar icon (platform-native badge API) | FRD CLR-024 | C++ Eng #2 | 3 | macOS Dock badge and Windows taskbar badge show violation count; updates in real time |
| 2-4-7 | Implement project-open performance optimisation: lazy-load silhouettes not visible at startup zoom | TRD-PERF-008 | Lead C++ Eng | 5 | 100-aircraft .arld file opens in ≤ 1 s on minimum hardware; all items available after pan |
| 2-4-8 | UX research: analyse UAT 1 recordings; deliver mid-project UX report with improvement recommendations | Charter §14.1 UX | UX Designer | 5 | UX report delivered to PM; top 5 improvements added to Phase 2 backlog |
| 2-4-9 | Implement auto-update mechanism: check GitHub Releases for new library data version; download if user approves | Charter §3.2 Phase 2 | Lead C++ Eng | 5 | Update check fetches manifest over HTTPS; user sees changelog; download replaces old entries only |

| Sprint 2-5 | Dates Month 10–11, Wk 1–2 | Points 46 | Sprint Goal: UAT events 2 & 3; export quality review with print vendors |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 2-5-1 | Conduct UAT session at Airshow Event 2 (30-aircraft layout scenario); screen-capture | TRD-TEST-011 | QA Eng + Domain | 5 | Task completion rate ≥ 85%; session video archived |
| 2-5-2 | Conduct UAT session at Airshow Event 3 (30-aircraft layout scenario); screen-capture | TRD-TEST-011 | QA Eng + Domain | 5 | Task completion rate ≥ 85%; all three UAT events now complete |
| 2-5-3 | Compile aggregate UAT task completion statistics across 3 events; confirm ≥ 85% pass rate | Charter §13 KPI | PM + QA Eng | 3 | Written UAT Sign-Off Report filed confirming KPI met or gap identified |
| 2-5-4 | Submit PDF layouts to 3 commercial print vendors; evaluate proofs against checklist (scale, colour, font, bleed) | TRD-TEST-012 FRD EXP-016–017 | QA Eng + Domain | 5 | Print proofs evaluated; structured survey completed; 4.0/5.0 satisfaction threshold checked |
| 2-5-5 | Fix any print-vendor issues (ICC profile, bleed, colour shift); re-submit to vendors for approval | TRD-EXP-012 | Lead C++ Eng | 5 | All 3 vendors confirm acceptable print quality; no colour or font issues remain |
| 2-5-6 | Triage UAT Events 2–3 bugs; fix all P1 and P2 issues | Charter UAT | Lead C++ Eng + C++ Eng #2 | 8 | Zero P1 bugs; P2 bug list < 5 items; each fix covered by regression test |
| 2-5-7 | Run NPS survey on 25-user beta cohort; collect qualitative feedback | Charter §13 KPI NPS=40 | PM | 2 | Survey responses from ≥ 20 of 25 users; NPS score calculated |
| 2-5-8 | Performance benchmark full suite on all 3 platforms; commit results as release artifacts | TRD-PERF-001–010 | QA Eng | 5 | All 10 performance budgets pass on all 3 platforms; benchmark trend shows no regression from Sprint 2-1 |
| 2-5-9 | Implement scale bar variants: imperial only, metric only, dual; user selects per export | FRD EXP-015 | C++ Eng #2 | 3 | Scale bar in PDF and PNG reflects selected unit mode; dual shows both |
| 2-5-10 | Update NOTICES.txt; prepare draft LICENSES.txt for Phase 3 open-source audit | TRD-SEC-040 FRD PLAT-042–043 | QA Eng + Legal | 5 | NOTICES.txt generated at build; LICENSES.txt contains all SPDX identifiers; Legal review scheduled |

| Sprint 2-6 | Dates Month 11–12, Wk 3–4 | Points 44 | Sprint Goal: Security review, open-source license audit, Phase 2 hardening |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 2-6-1 | Complete formal open-source license audit (Legal + Lead Eng); confirm Apache 2.0 community edition compliance | FRD PLAT-043 TRD-SEC-040–042 | Lead C++ Eng + Legal | 8 | Audit report signed off by Legal; all dependencies in SPDX allowlist; no GPL in binaries |
| 2-6-2 | Complete security review: file-parsing limits, SVG sanitization, HTTPS enforcement, no telemetry without consent | TRD-SEC-001–005 | Lead C++ Eng + QA Eng | 8 | Security review report filed; all TRD-SEC requirements verified with test evidence |
| 2-6-3 | Run full performance benchmark suite; produce Phase 2 benchmark report for Phase 3 gate | TRD-PERF-001–010 | QA Eng | 5 | All 10 budgets met; Phase 2 Benchmark Report PDF generated |
| 2-6-4 | Resolve remaining P2 bugs from UAT; run full regression suite across all 3 platforms | Charter UAT | C++ Eng #2 + QA Eng | 8 | Zero P1/P2 open bugs; all CI tests pass on all 3 platforms |
| 2-6-5 | Write Phase 2 release notes; update README with build instructions and feature summary | Charter Phase 3 | PM + Lead C++ Eng | 3 | Release notes cover all features since alpha; README accurate and reviewed by 3 team members |
| 2-6-6 | Confirm NPS ≥ 40 from user survey; if not, schedule additional feedback sessions | Charter §13 KPI | PM | 2 | NPS score ≥ 40 confirmed; or remediation plan filed with steering committee |
| 2-6-7 | Prepare Phase 3 gate materials: UAT sign-off, benchmark report, security report, license audit, NPS result | Charter Phase Gate | PM | 5 | Phase 3 gate package assembled; steering committee review meeting scheduled |
| 2-6-8 | Fix any outstanding WCAG 2.1 AA accessibility issues identified in audits | TRD-A11Y-001–003 | UX Designer + C++ Eng #2 | 5 | Zero WCAG 2.1 AA critical issues remain; audit sign-off from UX Designer |

⭐ Phase 2 Gate — Beta Sign-Off (End of Month 12) - 150+ aircraft types in library; all entries pass CI schema validation - All export formats (SVG, PDF, PNG, JPEG, Batch) functional; golden-file CI test passing - UAT task completion rate ≥ 85% across 3 real airshow events (30-aircraft scenario) - PDF print quality: 3 vendors confirm 4.0/5.0 satisfaction; ICC profile and fonts correct - All 10 performance budgets (TRD-PERF-001 through -010) met on all 3 platforms - NPS ≥ 40 from beta user cohort - Security review and open-source license audit reports filed and signed off - Zero P1/P2 open bugs; WCAG 2.1 AA compliance verified

PHASE 3 — Desktop Launch Months 13–14 ¦ Sprints 3-1 and 3-2 ¦ Public v1.0 release, open-source community edition, commercial tier

| Sprint 3-1 | Dates Month 13, Wk 1–2 | Points 40 | Sprint Goal: Public v1.0 release on all platforms; GitHub community edition launch |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 3-1-1 | Create signed production release builds (.dmg, .AppImage, .deb, .msi) triggered by v1.0.0 tag; attach to GitHub Release | TRD-BUILD-008 FRD PLAT-030–034 | Lead C++ Eng + QA Eng | 8 | All 4 packages signed; GitHub Release v1.0.0 published; download links live |
| 3-1-2 | Publish community edition source to public GitHub repository; apply Apache 2.0 LICENSE; publish contributing guide and CLA | FRD PLAT-040 Charter §3.2 | PM + Lead C++ Eng | 5 | Public repo live; first external star/watch within 48 hours; CONTRIBUTING.md and CLA bot active |
| 3-1-3 | Publish project website / landing page (GitHub Pages): features, screenshots, download links, documentation | Charter Phase 3 | UX Designer + PM | 5 | Website live; download buttons link to GitHub Release artifacts; Google Analytics active |
| 3-1-4 | Submit ARLD listing to ICAS marketplace / resources page; notify ICAS Safety Committee | Charter §13 KPI Charter Phase 3 | PM | 3 | ICAS listing confirmed live; email acknowledgement from ICAS received |
| 3-1-5 | Implement adoption dashboard: GitHub Release download counts + opt-in telemetry event counter | Charter §13 KPI | Lead C++ Eng + PM | 5 | Dashboard shows install counts per platform; opt-in rate tracked |
| 3-1-6 | Publish ARLD v1.0 documentation site: user guide, aircraft library schema, .arld file format spec, FAQ | Charter Phase 3 | UX Designer + PM | 5 | Docs site live; user guide covers all 7 display types and all 4 export formats |
| 3-1-7 | Monitor GitHub Issues for v1.0 launch bugs; hotfix any P1 issues within 48 hours | Charter Phase 3 | Lead C++ Eng + QA Eng | 5 | Zero P1 issues unresolved > 48 hours; v1.0.1 hotfix released if any P1 found |
| 3-1-8 | Steering committee presentation: Phase 3 launch metrics, NPS, adoption counts, Phase 4 readiness | Charter §14.2 Governance | PM | 5 | Presentation delivered; Phase 4 adoption gate metrics baseline established |

| Sprint 3-2 | Dates Month 13–14, Wk 3–4 | Points 38 | Sprint Goal: Commercial license tier, ICAS marketplace, adoption monitoring |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 3-2-1 | Implement commercial desktop license tier: license key validation, feature unlock for commercial features (priority support, volume exports) | Charter Phase 3 Commercial | Lead C++ Eng | 8 | License key accepted in About dialog; commercial features unlocked; community edition unaffected |
| 3-2-2 | Set up commercial license distribution: Gumroad or Stripe payment link; license key delivery email | Charter Phase 3 Commercial | PM + Lead C++ Eng | 5 | Test purchase completes; license key delivered by email; key activates commercial features |
| 3-2-3 | Monitor adoption KPI: target 25 active events using ARLD within 6 months of launch; weekly reporting | Charter §13 KPI | PM | 3 | Weekly adoption report template running; first 5 events confirmed via survey or telemetry |
| 3-2-4 | Publish Phase 4 business case preparation materials: adoption metrics, NPS, Phase 4 cost estimate, steering committee deck | Charter Phase 4 Gate | PM | 5 | Business case draft circulated to Director of Airshow Operations and Finance; review meeting scheduled |
| 3-2-5 | Address top 5 community edition feature requests from GitHub Issues (P3/cosmetic) | Community Feedback | C++ Eng #2 | 8 | 5 community requests closed as fixed or declined with explanation; v1.1.0 patch released |
| 3-2-6 | Final Phase 3 retrospective; update project risk register; close Phase 0–3 budget actuals | Charter §14.2 | PM | 3 | Retrospective report filed; budget actuals within 10% of estimate; lessons-learned doc published |
| 3-2-7 | Begin Phase 4 team recruitment (web, cloud, TypeScript/React engineers) pending steering committee Phase 4 approval | Charter Phase 4 | PM | 3 | Job descriptions posted; recruiter briefed; hiring plan tied to Phase 4 approval timeline |
| 3-2-8 | 6-month post-launch KPI checkpoint: confirm adoption ≥ 25 events, NPS ≥ 40 for Phase 4 gate | Charter Phase 4 Gate | PM | 3 | Checkpoint report filed; Phase 4 gate pass/fail recommendation submitted to steering committee |

⭐ Phase 3 Gate — Desktop Launch (End of Month 14) / Phase 4 Initiation Criteria - v1.0.0 production release published to GitHub Releases on all 3 platforms - Apache 2.0 community edition source public on GitHub; CLA bot active - Commercial license tier live; payment processing functional - ICAS marketplace listing confirmed - 50+ active airshow events using ARLD v1.0 for primary ramp planning (6-month window) - NPS ≥ 40 from show directors (6-month post-launch survey) - Written Phase 4 business case approved by steering committee with dedicated funding - Phase 4 team recruitment underway or complete

PHASE 4 — SaaS Platform (Pending Steering Committee Approval) Relative months +1 to +8 ¦ Sprints 4-1 through 4-4 ¦ Cloud-hosted web application, user accounts, subscription billing

Phase 4 Notice: Phase 4 sprints cannot begin until the Phase 3 gate criteria are met and the steering committee approves the Phase 4 business case with dedicated funding. Sprint dates are relative to the Phase 4 kickoff date (designated month +0).

| Sprint 4-1 | Dates Month +1 to +2 | Points 48 | Sprint Goal: Architecture ADR, WebAssembly PoC vs REST benchmark, React canvas prototype |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 4-1-1 | Author Phase 4 Architecture Decision Record: benchmark WebAssembly (Emscripten) vs REST microservice on 100-aircraft edit workload; select strategy | TRD-SAAS-001 FRD SAAS-003 | Lead C++ Eng + Web Lead | 13 | ADR document filed in repo; benchmark results show latency and bundle size for both strategies; strategy selected |
| 4-1-2 | Scaffold TypeScript/React web application with Vite; configure ESLint, Prettier, Vitest | TRD-SAAS-003 | Web Lead | 3 | React app builds; Vitest smoke test passes; linting CI job green |
| 4-1-3 | Implement React canvas prototype: basic QGraphicsScene equivalent using HTML5 Canvas or Konva.js; pan and zoom | FRD SAAS-001 | Web Lead + Frontend Eng | 8 | Canvas pans and zooms smoothly in Chrome, Edge, Firefox, Safari (current + prior major versions) |
| 4-1-4 | Integrate geometry engine via selected strategy (WASM or REST); verify Minkowski sum result matches desktop output | TRD-SAAS-001 FRD SAAS-003 | Lead C++ Eng + Web Lead | 13 | Web canvas shows identical clearance zone polygon to desktop for same aircraft placement; test fixture passes |
| 4-1-5 | Set up AWS infrastructure: ECS Fargate cluster, ECR, S3 bucket, RDS PostgreSQL 16 Multi-AZ, Redis | TRD-SAAS-007 TRD-SAAS-010 | Cloud Eng | 8 | terraform apply succeeds; ECS task starts; RDS accessible; S3 bucket with SSE-S3 configured |
| 4-1-6 | Configure Auth0 tenant; implement JWT RS256 validation middleware in Fastify; protect /api/v1/ routes | TRD-SAAS-004 FRD SAAS-010–012 | Web Lead | 5 | Unauthenticated request returns HTTP 401; authenticated request with valid JWT returns HTTP 200 |

| Sprint 4-2 | Dates Month +2 to +4 | Points 52 | Sprint Goal: User accounts, project CRUD, cloud sync, team workspaces |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 4-2-1 | Implement user registration/login: email+password and OAuth 2.0 (Google, Microsoft) via Auth0; TLS 1.3 | FRD SAAS-010–012 | Web Lead | 5 | User can register and log in via email and Google OAuth; session uses TLS 1.3 |
| 4-2-2 | Implement MFA (TOTP via Auth0 Guardian); make optional but available to all users | FRD SAAS-013 | Web Lead | 3 | User can enrol TOTP; subsequent logins require OTP; recovery codes generated |
| 4-2-3 | Implement project CRUD API (/api/v1/projects): create, read, update, delete; S3 storage with pre-signed URLs | TRD-SAAS-005 FRD SAAS-030 | Backend Eng | 8 | Project file stored in S3 at {org_id}/{project_id}/{version_id}.arld with SSE-S3 AES-256; pre-signed URL expires in 15 min |
| 4-2-4 | Implement auto-save: web client POSTs JSON Patch diff to /api/v1/projects/{id}/edits ≤ 5 s debounce | TRD-SAAS-006 FRD SAAS-031 | Web Lead + Backend Eng | 8 | Edit diff applied server-side; concurrent edits resolved last-write-wins at field level; no data loss on disconnect |
| 4-2-5 | Implement team workspaces: create workspace, invite members by email, assign roles (Show Director, Ramp Coordinator, Read-Only) | FRD SAAS-020 FRD SAAS-021 | Backend Eng | 8 | Invited user receives email; accepts invite; can view workspace projects per assigned role |
| 4-2-6 | Implement read-only time-limited share link (24-hour expiry, no account required) | FRD SAAS-022 | Backend Eng | 5 | Share link opens read-only canvas in unauthenticated browser; link expires after 24 hours |
| 4-2-7 | Implement full audit log: user_id (UUID), timestamp, action type; PII excluded from logs; pgcrypto column-level encryption for email/org_name | TRD-SAAS-009 FRD SAAS-023 | Backend Eng | 8 | Audit log records every project edit; grep for email in logs returns zero results; pgcrypto functions active |
| 4-2-8 | Implement project archive export: .zip of all .arld files; user data portability | FRD SAAS-033 | Backend Eng | 3 | User can download .zip containing all their projects as .arld files; zip is valid |
| 4-2-9 | ECS auto-scaling: configure ALB RequestCountPerTarget > 1000 scale-out; min 2 tasks, max 50 | TRD-SAAS-007 | Cloud Eng | 5 | Load test: 1,200 concurrent requests → third task spins up within 60 seconds |

| Sprint 4-3 | Dates Month +4 to +6 | Points 50 | Sprint Goal: Stripe billing, SaaS feature parity with desktop, circuit breaker, beta SaaS launch |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 4-3-1 | Implement Stripe subscription billing: free community tier (3 projects, 500 MB) and Pro tier (unlimited); annual discount | FRD SAAS-040–043 TRD-SAAS-009 | Web Lead + Backend Eng | 8 | Test payment succeeds; Pro tier unlocks; no payment card data stored in ARLD DB; Stripe webhook verified |
| 4-3-2 | Implement circuit breaker (opossum) for REST geometry microservice calls; 50% error threshold; HTTP 503 + Retry-After | TRD-SAAS-008 | Backend Eng | 5 | Simulated geometry service failure → circuit opens after 50% error rate; clients receive 503 with Retry-After header |
| 4-3-3 | Implement SaaS feature parity: all 7 display types, all clearance rules, violation overrides, layout versioning, all 4 export formats in web UI | FRD SAAS-001 Charter SaaS parity | Web Lead + Frontend Eng | 13 | Web app produces identical SVG/PDF/PNG/JPEG output to desktop for same reference layout |
| 4-3-4 | Implement automated RDS failover test; confirm RTO ≤ 15 min; enable 14-day automated backups | TRD-SAAS-010 FRD SAAS-053 | Cloud Eng | 5 | Simulated primary AZ failure → app reconnects to replica within 15 min; no data loss; backup retention confirmed |
| 4-3-5 | Perform SaaS security audit and penetration test (external firm); remediate all critical and high findings | Charter Phase 4 budget | Cloud Eng + External | 13 | Penetration test report received; all critical/high findings remediated; retest passed |
| 4-3-6 | Launch beta SaaS (invite-only, 50 users); set up uptime monitoring (99.5% SLA target) | Charter Phase 4 Milestone | PM + Cloud Eng | 3 | 50 beta users active; uptime dashboard live; no outage > 15 min in first 2 weeks |
| 4-3-7 | Implement responsive design for tablet screens (minimum 1024×768); test on iPad and Android tablet | FRD SAAS-004 | Frontend Eng | 3 | Canvas usable on iPad 10th gen and Samsung Galaxy Tab S8; no horizontal scroll on 1024 px viewport |

| Sprint 4-4 | Dates Month +6 to +8 | Points 44 | Sprint Goal: Public SaaS v1.0 launch, 99.5% uptime SLA, post-launch monitoring |
| --- | --- | --- | --- |

| # | User Story / Task | FRD / TRD Refs | Owner(s) | Points | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| 4-4-1 | Implement desktop ↔ SaaS bidirectional sync: .arld projects started on desktop continue in browser and vice versa | FRD SAAS-032 | Web Lead + Lead C++ Eng | 13 | Round-trip: create layout on desktop → sync → open in browser → edit → sync back → open on desktop; no data loss |
| 4-4-2 | Public SaaS v1.0 launch: open registration; publish pricing page; announce to ICAS community | Charter Phase 4 Milestone | PM + Web Lead | 5 | Public registration open; first 100 free-tier sign-ups within first week; pricing page live |
| 4-4-3 | Confirm 99.5% uptime SLA during peak planning period (simulate October load test) | FRD SAAS-051 TRD-SAAS-007 | Cloud Eng + QA Eng | 8 | Load test: 10,000 concurrent sessions; P95 response time < 500 ms; uptime 99.5%+ over 30-day window |
| 4-4-4 | Implement SaaS KPI tracking: registered events, Pro conversions, NPS survey at 30-day mark | Charter §13 Phase 4 KPIs | PM | 3 | KPI dashboard live; first 30-day NPS survey sent; 100 registered events target tracked |
| 4-4-5 | Take manual RDS snapshot before production launch; confirm 14-day automated backups active | TRD-SAAS-010 | Cloud Eng | 2 | Manual snapshot exists pre-launch; automated backup schedule verified in AWS console |
| 4-4-6 | Phase 4 retrospective; finalise Phase 4 budget actuals; publish SaaS launch post-mortem | Charter §14.2 | PM | 3 | Retrospective report filed; budget within estimate; post-mortem published to engineering blog |
| 4-4-7 | Reach 100 registered events KPI (12-month target); or file remediation plan with steering committee | Charter §13 KPI SaaS 100 events | PM | 5 | 100 registered events milestone confirmed in dashboard; or growth-gap remediation plan filed |
| 4-4-8 | Post-launch security monitoring: enable AWS GuardDuty, CloudTrail, WAF rules; set up PagerDuty on-call rotation | TRD-SAAS-007 Charter Security | Cloud Eng | 5 | GuardDuty active; CloudTrail logs shipping to S3; on-call rotation confirmed with < 5 min escalation |

⭐ Phase 4 Launch Criteria (Month +8) - Public SaaS v1.0 live; open registration; pricing page published - 99.5% uptime confirmed over rolling 30-day window - 10,000 concurrent session load test passed (P95 response < 500 ms) - Desktop ⇔ SaaS bidirectional sync functional; round-trip data integrity verified - External penetration test passed; all critical/high findings remediated - 100 registered events target tracked (12-month KPI runway established) - AWS GuardDuty, CloudTrail, and WAF active; on-call rotation in place

# Velocity and Capacity Summary

The table below summarises planned story points, team size, and key outcomes per sprint across all phases. Phase 4 team size is indicative pending Phase 4 staffing plan.

| Sprint | Planned Pts | Team Size | Velocity | Key Outcome |
| --- | --- | --- | --- | --- |
| Sprint 0-1 | 30 | 2.0 FTE | 30 | Repository + CI green on all 3 platforms |
| Sprint 0-2 | 34 | 2.5 FTE | 34 | Interactive Qt canvas with pan, zoom, snap grid |
| Sprint 0-3 | 36 | 3.25 FTE | 36 | 20-aircraft library; drag-and-drop placement |
| Sprint 0-4 | 35 | 3.25 FTE | 35 | CGAL clearance zones; real-time violation detection |
| Sprint 0-5 | 32 | 3.25 FTE | 32 | SVG export; JSON save/load; PoC gate signed off |
| Sprint 1-1 | 46 | 6.25 FTE | 46 | Production refactor; installers; 50-entry library |
| Sprint 1-2 | 44 | 6.25 FTE | 44 | Violations panel; clearance rules; display types |
| Sprint 1-3 | 47 | 6.25 FTE | 47 | Library browser; custom aircraft; 75-entry library |
| Sprint 1-4 | 44 | 6.25 FTE | 44 | Tail-swing, gear variants, accessibility foundation |
| Sprint 1-5 | 45 | 6.25 FTE | 45 | PDF export (libharu); satellite underlay |
| Sprint 1-6 | 43 | 6.25 FTE | 43 | PNG/JPEG export; alpha release to 10 beta users |
| Sprint 2-1 | 50 | 6.25 FTE | 50 | 150-type library; batch export; SVG layers |
| Sprint 2-2 | 44 | 6.25 FTE | 44 | Layout versioning; delta view; minimap; tiles |
| Sprint 2-3 | 47 | 6.25 FTE | 47 | Library updates; LOD rendering; beta release |
| Sprint 2-4 | 44 | 6.25 FTE | 44 | UAT Event 1; P1 bug fixes; group move polish |
| Sprint 2-5 | 46 | 6.25 FTE | 46 | UAT Events 2–3; print vendor review |
| Sprint 2-6 | 44 | 6.25 FTE | 44 | Security review; license audit; Phase 2 hardening |
| Sprint 3-1 | 40 | 5.0 FTE | 40 | v1.0 public release; community edition GitHub launch |
| Sprint 3-2 | 38 | 5.0 FTE | 38 | Commercial tier; ICAS listing; Phase 4 prep |
| Sprint 4-1 | 48 | 6.0 FTE* | 48 | ADR; WASM/REST benchmark; React canvas PoC |
| Sprint 4-2 | 52 | 7.0 FTE* | 52 | Auth; project CRUD; cloud sync; workspaces |
| Sprint 4-3 | 50 | 7.0 FTE* | 50 | Stripe billing; SaaS parity; beta SaaS launch |
| Sprint 4-4 | 44 | 7.0 FTE* | 44 | Desktop sync; public SaaS v1.0; uptime SLA |

* Phase 4 team size is indicative; finalised as part of the Phase 4 staffing plan approved at Phase 3 gate.

| Phase | Total Sprints | Total Planned Points | Duration |
| --- | --- | --- | --- |
| Phase 0 — C++ PoC | 5 | 167 | 10 weeks (Weeks 1–10) |
| Phase 1 — Foundation | 6 | 269 | 4 months (Months 3–6) |
| Phase 2 — Complete Desktop | 6 | 275 | 6 months (Months 7–12) |
| Phase 3 — Desktop Launch | 2 | 78 | 2 months (Months 13–14) |
| Phase 4 — SaaS (pending) | 4 | 194 | 8 months relative to Phase 4 kickoff |
| TOTAL (Phases 0–3) | 19 | 789 | ~14 months calendar |
| TOTAL (all phases) | 23 | 983 | ~22 months calendar |

# Authorization and Approval

By signing below, the undersigned approve this Project Plan as the governing sprint schedule for the Airshow Ramp Layout Designer project.

| _________________________________ Director of Airshow Operations Signature / Date | _________________________________ Program Management Officer Signature / Date | _________________________________ Lead Systems Engineer Signature / Date |
| --- | --- | --- |

— End of Document —